## All Projects-All Status
Data as of 3/11/2025
Permit Name | Permit Number | Project Status | Permit Type | Megawatts | Total Acres | Agricultural Land Acres | Pollinator Acres | Forestry Acres | Disturbance Zone Acres | Section 130 Permit | Mitigation Plan | County | Brownfield Site | Permit Coordinator | NOI Received | NOI Resubmittal Date(s) | NOI Withdrawn | Application Received | Application Incomplete | Supplemental Info from Applicant | Public Meeting Date | PBR Authorization Letter | PBR Modification Materials Received | PBR Modification Issued | Construction Commenced | Commercial Operation Commenced
1650 Cumberland Site 2 | RE0000301 | Permit - Active | Solar | 2 | 100 |  |  |  | 12 | YES | No | Cumberland County | No | Amber K Foster | 2023-10-24 |  |  | 2023-10-24 |  |  |  | 2023-10-25
1650 Cumberland Solar Facility | RE0000249 | Permit - Active | Solar | 3 | 101 |  |  |  | 20 | YES |  | Cumberland County | No | Susan M Tripp | 2022-10-21 |  |  | 2022-10-20 | 2022-10-27 |  |  | 2023-01-05
1671 Cumberland Solar Facility | RE0000248 | Permit - Active | Solar | 3 | 66 |  |  |  | 36 | YES |  | Prince Edward County | No | Susan M Tripp | 2022-10-21 |  |  | 2022-11-03 |  |  |  | 2022-11-03
2188 Poorhouse Road Solar | RE0000254 | Permit - Active | Solar | 3 | 76 |  |  |  | 23 | YES |  | Lunenburg County | No | Amber K Foster | 2022-11-03 |  |  | 2022-11-03 |  |  |  | 2022-11-07
360 Solar Center Project | RE0000235 | Permit - Active | Solar | 52 | 800 |  |  |  | 450 | No | YES | Chesterfield County | No | Amber K Foster | 2022-07-19 |  |  | 2024-04-29 |  | 2024-05-08 | 2024-04-17 | 2024-07-15
Aditya Solar | RE0000186 | Permit - Active | Solar | 11 | 90 |  |  |  | 60 | No | No | Louisa County | No | Mary (Beth) E Major | 2021-01-15 |  |  | 2022-03-24 |  |  | 2022-03-07 | 2022-06-03 |  |  |  | 2023-08-21
Altavista Solar LLC (FKA Dragonfly) | RE0000088 | Permit - Active | Solar | 80 | 1200 | 0 |  | 0 | 0 | No | YES | Campbell County | No | Mary (Beth) E Major | 2018-09-12 |  |  | 2019-05-31 |  |  |  | 2019-08-08 |  |  | 2020-03-11 | 2021-06-04
Alton Post Office Solar, LLC | RE0000065 | Permit - Active | Solar | 75 | 768 | 0 |  | 0 | 501 | No | No | Halifax County | No | Mary (Beth) E Major | 2017-10-06 |  |  | 2020-09-15 |  |  |  | 2020-12-07 |  |  | 2023-09-20 | 2024-12-24
Amelia Solar Buckskin Creek Road | RE0000334 | NOI - Active | Solar | 106 | 1100 |  |  |  | 750 | No |  | Amelia County | No | Amber K Foster | 2024-10-25
Amherst Mays Solar Farm | RE0000193 | Permit - Active | Solar | 4.9 | 50 |  |  |  | 25 | YES |  | Amherst County | No | Mary (Beth) E Major | 2021-01-26 |  |  | 2022-04-27 |  |  |  | 2022-05-03
Apple Grove Solar | RE0000162 | Permit - Active | Solar | 15 | 225 |  |  |  | 111 | No | YES | Louisa County | No | Susan M Tripp | 2020-05-22 |  |  | 2021-11-09 |  | 2022-02-18 |  | 2022-03-18 |  |  | 2023-03-27 | 2023-12-29
Ash Camp Solar, LLC | RE0000131 | Permit - Active | Solar | 1.6 | 11 |  |  |  |  | YES | No | Charlotte County | No | Mary (Beth) E Major | 2018-05-11 | [6 empty] | 2018-06-11
Augusta CSG LLC | RE0000244 | Permit - Active | Solar | 2.9 | 50 |  |  |  | 12 | YES |  | Augusta County | No | Susan M Tripp | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Axton Solar | RE0000111 | Permit - Active | Solar | 66 | 600 | 0 |  | 0 | 547 | No | YES | Henry County | No | Susan M Tripp | 2019-08-28 |  |  | 2022-03-23 |  |  | 2022-03-08 | 2022-06-17 |  |  | 2022-10-03 | 2023-12-28
BARC Community Solar Project | RE0000132 | Permit - Active | Solar | 0.5 | 5 |  |  |  |  | YES | No | Bath County | No | Mary (Beth) E Major | 2015-11-13
Bartonsville Energy Facility II, LLC | RE0000221 | Permit - Active | Solar | 50 | 478 |  |  |  | 407 | No | YES | Frederick County | No | Susan M Tripp | 2022-02-17 |  |  | 2022-06-21 | 2022-09-14 | 2022-09-16 | 2022-06-06 | 2022-09-23 |  |  | 2022-09-26
Bartonsville Energy Facility, LLC | RE0000158 | Permit - Active | Solar | 80 | 1160 |  |  |  | 869 | No | No | Frederick County | No | Mary (Beth) E Major | 2020-03-18 | 2020-10-14 |  | 2021-08-16 |  |  |  | 2021-11-01
Bedford Solar Center | RE0000146 | Permit - Active | Solar | 70 | 566 |  |  |  | 410 | No | No | Chesapeake City | No | Mary (Beth) E Major | 2019-11-20 |  |  | 2020-01-14 |  |  |  | 2020-04-09 |  |  | 2020-07-30 | 2021-11-23
Bedford Solar Center, LLC | RE0000089 | NOI - Withdrawn | Solar | 70 | 475 | 0 |  | 0 | 0 | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2018-09-21 |  | 2019-08-15
Bedford Solar, LLC | RE0000133 | Permit - Active | Solar | 3 | 100 |  |  |  | 22 | YES | No | Bedford County | No | Mary (Beth) E Major | 2017-03-13 | [6 empty] | 2017-03-23
Belcher Solar, LLC | RE0000028 | Permit - Active | Solar | 88.2 | 1305 | 0 |  | 0 | 0 | No | YES | Louisa County | No | Mary (Beth) E Major | 2016-10-28 |  |  | 2017-06-20 |  |  |  | 2017-08-08 |  |  | 2020-01-14 | 2021-06-30
Belcher Solar, LLC - Expansion Project | RE0000126 | NOI - Withdrawn | Solar | 17 | [5 empty] | No | YES | Louisa County | No | Mary (Beth) E Major | 2019-03-11 |  | 2019-09-20
Bella Terra Solar | RE0000213 | Permit - Active | Solar | 100 | 1056 |  |  |  | 558 | No | YES | Pulaski County | No | Amber K Foster | 2021-12-06 |  |  | 2023-02-17 | 2023-04-14 | 2023-08-25 | 2022-10-18 | 2023-10-24 | 2024-11-11 | 2025-01-10
Big Pine Solar | RE0000340 | NOI - Active | Solar | 150 | 2187 |  |  |  | 1050 | No |  | Sussex County | No | Matthew A Snow | 2024-12-02
Birchwood Renewables, LLC | RE0000201 | NOI - Active | Solar | 55 | 640 |  |  |  |  | No |  | King George County | YES | Mary (Beth) E Major | 2021-06-21
Black Bear Solar, LLC | RE0000197 | Permit - Terminated without Cause | Solar | 1.6 | 13 |  |  |  |  | YES |  | Buckingham County | No | Mary (Beth) E Major | 2021-02-19 |  |  | 2021-02-19 |  |  |  | 2021-04-02
Blue Orchard Solar | RE0000208 | NOI - Active | Solar | 10 | 96 |  |  |  |  | No |  | Carroll County | No | Mary (Beth) E Major | 2021-10-05
Blue Rock Solar | RE0000298 | Permit - Active | Solar | 100 | 596 |  |  |  | 1127 | No | No | Buckingham County | No | Amber K Foster | 2023-09-19 |  |  | 2024-12-27 |  |  | 2024-08-27 | 2025-02-06
Bluestone Farm Solar, LLC | RE0000014 | Permit - Active | Solar | 50 | 333 | 0 |  | 0 | 0 | No | No | Mecklenburg County | No | Mary (Beth) E Major | 2016-05-13 |  |  | 2017-10-25 |  |  |  | 2017-12-05 |  |  | 2019-03-01 | 2021-06-01
BM&D Ltd. | RE0000031 | NOI - Active | Solar | 40 | 320 | 0 |  | 0 | 0 | No | No | Pulaski County | No | Mary (Beth) E Major | 2016-12-21
Bookers Mill Solar | RE0000196 | Permit - Active | Solar | 127 | 1600 |  |  |  | 640 | No |  | Richmond County | No | Mary (Beth) E Major | 2021-03-10 |  |  | 2021-09-01 |  |  |  | 2021-11-29 |  |  | 2022-08-01
Bookers Mill Solar, LLC | RE0000170 | NOI - Withdrawn | Solar | 127 | 1000 |  |  |  |  | No | No | Richmond County | No | Mary (Beth) E Major | 2020-06-11 |  | 2021-03-10
Boston Hill Solar Project | RE0000327 | NOI - Active | Solar | 115 | 1066 |  |  |  | 600 | No |  | Cumberland County | No | Amber K Foster | 2024-08-07
Bowie Road Solar, LLC | RE0000322 | Permit - Active | Solar | 5 | 20 |  |  |  |  | YES |  | Westmoreland County | No | Matthew A Snow | 2024-07-15 |  |  | 2024-07-15 |  |  |  | 2024-07-17
Brandy Station | RE0000034 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Culpeper County | No | Mary (Beth) E Major | 2017-02-07 |  | 2017-10-31
Briel Farm Solar LLC | RE0000039 | Permit - Active | Solar | 20 | 230 | 0 |  | 0 | 105 | No | YES | Henrico County | No | Mary (Beth) E Major | 2017-02-15 |  |  | 2018-04-11 |  | 2018-06-13 |  | 2018-06-14 | 2020-01-17 | 2020-03-10 |  | 2021-03-02
Buchanan County Solar Project | RE0000346 | Permit - Active | Solar | 75 | 1188 |  |  |  |  | YES | No | Buchanan County | YES | Amber K Foster | 2025-02-27 |  |  | 2025-02-27 | 2025-02-27 |  |  | 2025-03-03
Buckhorn Mountain Solar Project | RE0000207 | NOI - Active | Solar | 16.5 | 465 |  |  |  |  | No |  | Tazewell County | No | Mary (Beth) E Major | 2021-10-01
Buckingham II Solar LLC | RE0000063 | Permit - Active | Solar | 20 | 295 | 0 |  | 0 | 225 | No | No | Buckingham County | No | Mary (Beth) E Major | 2017-07-25 |  |  | 2018-02-20 | 2018-03-29 |  |  | 2018-06-18 |  |  | 2020-10-07 | 2021-07-28
Buckingham Solar I, LLC | RE0000005 | Permit - Active | Solar | 19.8 | 302 | 0 |  | 0 | 200 | No | No | Buckingham County | No | Mary (Beth) E Major | 2016-02-18 |  |  | 2016-06-09 |  |  |  | 2016-08-09 |  |  | 2017-05-13 | 2017-11-30
Bumblebee Solar, LLC | RE0000072 | NOI - Active | Solar | 15 | 544 | 0 |  | 0 | 260 | No | No | Campbell County | No | Mary (Beth) E Major | 2017-11-08
Cabin Point Solar Center | RE0000152 | NOI - Active | Solar | 75 | 700 |  |  |  | 488 | No | No | Sussex County | No | Mary (Beth) E Major | 2020-02-18
Caden Energix Hickory, LLC | RE0000083 | Permit - Active | Solar | 32 | 154 | 0 |  | 0 | 145 | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2018-08-02 |  |  | 2018-11-26 |  | 2019-01-21 |  | 2019-03-14 |  |  |  | 2020-08-18
Caden Energix Jarratt LLC | RE0000112 | NOI - Active | Solar | 82.5 | 695 | 0 |  | 0 | 0 | No | No | Greensville County | No | Mary (Beth) E Major | 2019-08-28
Caden Energix New Kent, LLC | RE0000151 | NOI - Active | Solar | 20 | 540 |  |  |  |  | No | No | New Kent County | No | Mary (Beth) E Major | 2020-01-24
Caden Energix Piney River LLC | RE0000154 | NOI - Withdrawn | Solar | 50 | 389 |  |  |  |  | No | No | Amherst County | No | Mary (Beth) E Major | 2020-02-23 |  | 2023-09-06
Caden Energix Spout Spring LLC | RE0000097 | NOI - Active | Solar | 60 | 375 | 0 |  | 0 | 0 | No | No | Appomattox County | No | Mary (Beth) E Major | 2018-11-14
Caden Energix Wytheville LLC | RE0000113 | Permit - Active | Solar | 20 | 154 | 0 |  | 0 | 139 | No | No | Wythe County | No | Mary (Beth) E Major | 2019-08-28 |  |  | 2020-06-03 |  |  | 2020-05-05 | 2020-07-27 |  |  | 2021-09-27 | 2022-06-03
Campari Solar, LLC | RE0000180 | NOI - Withdrawn | Solar | 15.6 | 141 |  |  |  |  | No |  | Orange County | No | Mary (Beth) E Major | 2020-12-04 |  | 2022-04-11
Carey and Peyton 5 | RE0000280 | Permit - Active | Solar | 5 | 56 |  |  |  | 39 | YES | No | Westmoreland County | No | Amber K Foster | 2023-03-17 |  |  | 2023-03-17 |  |  |  | 2023-03-27
Carver Solar I | RE0000305 | Permit - Active | Solar | 91 | 1138 |  |  |  | 637 | No | YES | Isle of Wight County | No | Amber K Foster | 2024-01-16 |  |  | 2024-11-22 |  | 2025-01-03 | 2024-11-07 | 2025-01-31
Carvers Creek Solar | RE0000145 | Permit - Active | Solar | 150 | 2400 |  |  |  | 1734 | No | YES | Gloucester County | No | Mary (Beth) E Major | 2019-11-22 |  |  | 2020-08-18 |  |  |  | 2020-11-12 |  |  | 2022-10-01 | 2024-12-23
Carysbrook Solar | RE0000245 | Permit - Terminated without Cause | Solar | 3 | 360 |  |  |  | 40 | YES | No | Fluvanna County | No | Amber K Foster | 2022-10-18 |  |  | 2022-10-18 |  |  |  | 2022-10-28
Centerville Pike Solar Project, LLC | RE0000010 | NOI - Withdrawn | Solar | 15 | 245 | 0 |  | 0 | 0 | No | No | Chesapeake City | No | Mary (Beth) E Major | 2016-04-05 |  | 2019-08-15
Centerville South Solar | RE0000281 | Permit - Active | Solar | 5 | 39 |  |  |  | 31 | YES | No | Chesapeake City | No | Amber K Foster | 2023-03-21 |  |  | 2023-03-21 |  |  |  | 2023-03-27
Centerville Turnpike Solar Facility | RE0000250 | Permit - Active | Solar | 3 | 49 |  |  |  | 29 | YES |  | Chesapeake City | No | Susan M Tripp | 2022-11-03 |  |  | 2022-11-03 |  |  |  | 2023-01-05
Chaberton Solar Leatherman | RE0000315 | Permit - Active | Solar | 5 | 40 |  |  |  | 18 | YES | No | Hanover County | No | Amber K Foster | 2024-05-29 |  |  | 2024-05-29 | 2024-06-03 |  |  | 2024-12-16
Chesapeake Solar Project, LLC | RE0000006 | Permit - Active | Solar | 118 | 940 | 0 |  | 0 | 0 | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2018-06-15 |  |  | 2021-11-02 |  |  | 2021-10-15 | 2022-01-14 |  |  | 2022-11-11 | 2023-12-20
Chesapeake Solar, LLC | RE0000080 | NOI - Withdrawn | Solar | 20 | 250 |  |  |  |  | No |  | Chesapeake City | No | Mary (Beth) E Major | 2016-02-23 |  | 2016-09-29
Chester Solar Technology Park, LLC | RE0000156 | NOI - Active | Solar | 150 | 1675 |  |  |  |  | No | No | Chesterfield County | No | Mary (Beth) E Major | 2020-03-18
Children of Chesterfield Solar | RE0000094 | NOI - Active | Solar | 20 | 165 | 0 |  | 0 | 135 | No | No | Chesterfield County | No | Mary (Beth) E Major | 2018-10-16
Church View Solar, LLC | RE0000076 | Permit - Terminated without Cause | Solar | 20 | 535 | 0 |  | 0 | 0 | No | YES | Middlesex County | No | Mary (Beth) E Major | 2017-12-06 |  |  | 2018-02-02 | 2018-03-29 | 2018-04-30 |  | 2018-06-21
Colonial Solar | RE0000230 | NOI - Active | Solar | 7 | 90 |  |  |  |  | No |  | Prince William County | No | Susan M Tripp | 2022-05-27
Colonial Trail West Solar, LLC | RE0000032 | NOI - Withdrawn | Solar | 150 | 1250 | 0 |  | 0 | 0 | No | YES | Surry County | No | Mary (Beth) E Major | 2017-01-05 |  | 2017-03-14
Core Solar SPV XIII, LLC | RE0000050 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2017-05-23 |  | 2018-06-15
Correctional Solar, LLC | RE0000016 | Permit - Active | Solar | 20 | 1690 | 0 |  | 0 | 460 | No | YES | Gloucester County | No | Mary (Beth) E Major | 2016-05-30 |  |  | 2016-08-29 |  |  |  | 2016-10-17 |  |  | 2017-05-01 | 2017-11-29
Courthouse Hwy Solar 1 | RE0000309 | Permit - Active | Solar | 3 | 14 |  |  |  | 5 | YES | No | Isle of Wight County | No | Amber K Foster | 2024-02-16 |  |  | 2024-02-14 | 2024-02-16 |  |  | 2024-02-23
Cow Creek Solar, LLC | RE0000194 | Permit - Active | Solar | 1 | 9 |  |  |  |  | YES |  | Gloucester County | No | Mary (Beth) E Major | 2021-01-04 |  |  | 2021-01-04 |  |  |  | 2021-04-02
Cox Energy Storage Project | RE0000287 | NOI - Active | Energy Storage | 8 | 1 |  |  |  |  | No |  | Cumberland County | No | Amber K Foster | 2023-05-26
Crystal Hill Solar, LLC | RE0000066 | Permit - Active | Solar | 65 | 629 | 0 |  | 0 | 0 | No | No | Halifax County | No | Mary (Beth) E Major | 2017-10-06 |  |  | 2019-10-09 |  |  |  | 2019-12-17 |  |  | 2023-03-08 | 2023-12-29
Culpeper North Solar, LLC | RE0000070 | NOI - Active | Solar | 20 | 395 | 0 |  | 0 | 296 | No | No | Culpeper County | No | Mary (Beth) E Major | 2017-10-31
Cumberland Solar Project | RE0000326 | NOI - Active | Solar | 100 | 1794 |  |  |  | 900 | No |  | Cumberland County | No | Amber K Foster | 2024-08-07
Cunningham Solar, LLC | RE0000205 | Permit - Active | Solar | 5 | 62 |  |  |  | 30 | YES |  | Fluvanna County | No | Mary (Beth) E Major | 2021-06-02 | [6 empty] | 2021-08-06
CVE Johnson North | RE0000297 | Permit - Active | Solar | 3 | 110 |  |  |  | 24 | YES | No | Suffolk City | No | Amber K Foster | 2023-09-15 |  |  | 2023-09-15 |  |  |  | 2023-09-22
CVE Johnson South | RE0000296 | Permit - Active | Solar | 5 | 137 |  |  |  | 29 | YES | No | Suffolk City | No | Amber K Foster | 2023-09-15 |  |  | 2023-09-15 |  |  |  | 2023-09-22
CVE Murphy Solar Project | RE0000313 | Permit - Active | Solar | 2.6 | 13 |  |  |  |  | YES | No | Petersburg City | No | Amber K Foster |  |  |  | 2024-05-15 | 2024-05-21 |  |  | 2024-05-22
Danville BESS 1 | RE0000240 | Permit - Active | Energy Storage | 10.5 | 1 |  |  |  |  | YES | No | Danville City | No | Susan M Tripp | 2022-08-09 |  |  | 2022-08-09 |  |  |  | 2022-10-14 |  |  | 2022-02-28
Danville Farm, LLC | RE0000084 | Permit - Active | Solar | 12 | 191 | 0 |  | 0 | 0 | No | No | Pittsylvania County | No | Mary (Beth) E Major | 2018-08-09 |  |  | 2019-05-09 |  |  |  | 2019-07-10 |  |  | 2019-12-15 | 2020-08-26
Depot Solar | RE0000090 | Permit - Active | Solar | 15 | 150 | 150 |  | 0 | 0 | No | No | Campbell County | No | Mary (Beth) E Major | 2018-09-21 |  |  | 2019-08-27 |  |  |  | 2019-11-05 |  |  |  | 2022-07-15
Dept. of Veterans Affairs Medical Center | RE0000137 | Permit - Active | Solar | 1.7 | 6 |  |  |  |  | YES | No | Salem City | No | Mary (Beth) E Major | 2013-07-02 | [6 empty] | 2013-07-09
DG Revolution Solar | RE0000325 | Permit - Active | Solar | 5 | 101 |  |  |  | 38 | YES |  | Richmond County | No | Amber K Foster | 2024-07-17 |  |  | 2024-07-17 | 2024-07-18 |  |  | 2024-07-19
Dogwood Lane Solar | RE0000262 | Permit - Active | Solar | 4 | 33 |  |  |  |  | YES | No | Lunenburg County | No | Amber K Foster | 2022-11-29 |  |  | 2022-11-29 |  |  |  | 2022-12-08
Dogwood Solar | RE0000107 | Permit - Terminated without Cause | Solar | 20 | 350 | 0 |  | 0 | 178 | No | YES | Page County | No | Mary (Beth) E Major | 2019-06-14 |  |  | 2021-10-12 |  |  |  | 2022-01-14
Dry Fork Solar 1 | RE0000270 | Permit - Active | Solar | 3 | 47 |  |  |  | 21 | YES | No | Pittsylvania County | No | Amber K Foster | 2023-01-18 |  |  | 2023-01-18 |  |  |  | 2023-01-24
E2C Solar | RE0000138 | Permit - Active | Solar | 1.3 | 9 |  |  |  |  | YES | No | Montgomery County | No | Mary (Beth) E Major | 2017-07-12 | [6 empty] | 2017-07-12
Eastern Shore Solar, LLC | RE0000001 | Permit - Active | Solar | 80 | 1003 | 0 |  | 0 | 942 | No | YES | Accomack County | No | Mary (Beth) E Major | 2014-10-14 |  |  | 2015-06-08 |  |  |  | 2015-09-28 |  |  | 2015-09-28 | 2016-10-30
Elam Road Solar | RE0000303 | Permit - Active | Solar | 3 | 135 |  |  |  | 33 | YES | No | Prince Edward County | No | Amber K Foster | 2023-10-19 |  |  | 2023-10-19 |  |  |  | 2023-11-17
Endless Caverns North | RE0000227 | Permit - Active | Solar | 15.7 | 171 |  |  |  | 105 | No | YES | Rockingham County | No | Susan M Tripp | 2022-05-06 |  |  | 2022-12-12 |  | 2023-03-03 | 2022-11-29 | 2023-03-14 |  |  | 2023-05-22 | 2024-03-12
Endless Caverns Solar | RE0000077 | NOI - Withdrawn | Solar | 32 | 243 | 0 |  | 0 | 0 | No | No | Rockingham County | No | Mary (Beth) E Major | 2017-12-21 |  | 2022-04-18
Endless Caverns South | RE0000232 | Permit - Active | Solar | 15.7 | 142 |  |  |  | 99 | No | YES | Rockingham County | No | Susan M Tripp | 2022-05-06 |  |  | 2022-12-08 |  | 2023-03-03 | 2022-11-21 | 2023-03-14 |  |  | 2023-05-22 | 2024-03-05
Energix Nokesville, LLC | RE0000061 | Permit - Active | Solar | 20 | 300 | 0 |  | 0 | 0 | No | YES | Prince William County | No | Mary (Beth) E Major | 2017-07-25 |  |  | 2019-05-21 | 2019-07-30 | 2019-12-17 |  | 2020-02-20 |  |  | 2021-10-26 | 2022-11-22
Essex Solar Center LLC | RE0000007 | Permit - Active | Solar | 20 | 419 | 0 |  | 0 | 174 | No | YES | Essex County | No | Mary (Beth) E Major | 2016-03-02 |  |  | 2016-10-11 |  |  |  | 2016-12-07 | 2019-12-04 | 2020-03-05 | 2017-05-12 | 2017-12-14
Evergreen Energy Center | RE0000307 | NOI - Active | Energy Storage | 20 | 3 |  |  |  |  | YES |  | Loudoun County | No | Amber K Foster
Exmore Energy Storage EXENST10MW | RE0000341 | Permit - Active | Energy Storage | 10 | 2 |  |  |  | 1 | YES | No | Northampton County | No | Matthew A Snow | 2024-12-02 |  |  | 2024-12-02 | 2024-12-02 |  |  | 2025-01-24
Fairfax Landfill Solar | RE0000331 | Permit - Active | Solar | 5 | 40 |  |  |  | 31 | YES |  | Fairfax County | YES | Amber K Foster | 2024-09-05 |  |  | 2024-09-05 |  |  |  | 2024-10-03
Fairfield Lee Solar | RE0000260 | Permit - Active | Solar | 5 | 46 |  |  |  | 29 | YES | No | Rockbridge County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Fairy Stone Solar | RE0000218 | NOI - Active | Solar | 12 | 316 |  |  |  | 169 | No |  | Patrick County | No | Mary (Beth) E Major | 2021-12-10
First Solar Development, LLC | RE0000041 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Montgomery County | No | Mary (Beth) E Major | 2017-03-06 |  | 2019-03-19
Fisher Chewning Solar | RE0000224 | Permit - Active | Solar | 150 | 1620 |  |  |  | 1365 | No | YES | Louisa County | No | Susan M Tripp | 2022-04-04 |  |  | 2022-09-22 |  | 2022-06-21 | 2022-06-01 | 2022-09-21
Fluvanna Middle School Solar Facility | RE0000217 | NOI - Active | Solar | 0.7 | 7 |  |  |  |  | YES |  | Fluvanna County | No | Mary (Beth) E Major | 2021-12-13
Fort Powhatan Solar, LLC | RE0000115 | NOI - Withdrawn | Solar | 150 | 2000 | 0 |  | 0 | 0 | No | YES | Prince George County | No | Mary (Beth) E Major | 2018-04-11 |  | 2019-10-09
Fort Powhatan Solar, LLC | RE0000125 | Permit - Active | Solar | 150 | 3086 |  |  |  | 2000 | No | YES | Prince George County | No | Mary (Beth) E Major | 2019-10-07 |  |  | 2020-01-09 |  |  |  | 2020-03-19 |  |  | 2020-08-03 | 2022-01-19
Fountain Creek Solar | RE0000102 | NOI - Withdrawn | Solar | 80 | 802 | 0 |  | 0 | 0 | No | No | Greensville County | No | Mary (Beth) E Major | 2019-02-19 |  | 2021-01-07
Foxglove Solar, LLC | RE0000172 | Permit - Active | Solar | 75 | 672 |  |  |  | 408 | No | YES | Frederick County | No | Mary (Beth) E Major | 2020-08-28 |  |  | 2021-04-19 |  | 2021-06-07 |  | 2021-08-04 | 2022-05-02 | 2022-07-26 | 2023-08-21 | 2024-10-10
Foxhound Solar | RE0000095 | Permit - Active | Solar | 83 | 1125 | 0 |  | 0 | 600 | No | YES | Halifax County | No | Mary (Beth) E Major | 2018-10-26 |  |  | 2019-09-11 |  |  | 2019-07-02 | 2019-12-17 | 2020-01-15 | 2020-01-16 | 2023-01-17
Front Royal Solar Field | RE0000139 | Permit - Active | Solar | 2.5 | 20 |  |  |  | 15 | YES | No | Warren County | No | Mary (Beth) E Major | 2016-09-06 | [6 empty] | 2016-09-06 |  |  |  | 2017-03-31
Gardy's Mill Solar, LLC | RE0000043 | Permit - Active | Solar | 14 | 199 | 0 |  | 0 | 0 | No | No | Westmoreland County | No | Mary (Beth) E Major | 2017-04-18 |  |  | 2018-09-05 |  |  |  | 2018-11-27 |  |  |  | 2020-12-01
Gateway Grid Battery Storage Facility Project | RE0000329 | Application - In Review | Energy Storage | 100 | 51 |  |  |  | 14 | No |  | Botetourt County | No | Amber K Foster | 2024-09-24 |  |  | 2025-02-13 | 2025-02-14
Gladys Solar LLC | RE0000299 | Permit - Active | Solar | 60.4 | 1108 |  |  |  | 615 | No | YES | Campbell County | No | Amber K Foster | 2023-10-13 |  |  | 2024-01-25 | 2024-01-31 | 2024-03-07 |  | 2024-03-08
Gladys Solar Project | RE0000110 | NOI - Withdrawn | Solar | 60 | 1108 | 0 |  | 0 | 0 | No | No | Campbell County | No | Mary (Beth) E Major | 2019-08-28 |  | 2023-10-13
Gloucester Solar, LLC | RE0000048 | Permit - Active | Solar | 20 | 204 | 0 |  | 0 | 0 | No | YES | Gloucester County | No | Mary (Beth) E Major | 2017-04-27 |  |  | 2017-11-30 |  |  |  | 2018-02-12 | 2019-11-26 | 2020-03-19 | 2018-08-18 | 2019-04-22
Grassfield Solar LLC | RE0000109 | NOI - Withdrawn | Solar | 20 | 100 | 0 |  | 0 | 0 | No | No | Chesapeake City | No | Mary (Beth) E Major | 2019-07-10 |  | 2020-05-26
Grasshopper Solar, LLC | RE0000029 | Permit - Active | Solar | 80 | 927 | 0 |  | 0 | 913 | No | YES | Mecklenburg County | No | Mary (Beth) E Major | 2016-11-21 |  |  | 2019-05-09 |  |  |  | 2019-09-05 |  |  | 2019-09-25 | 2020-09-29
Green Acres Solar, LLC | RE0000176 | Permit - Active | Solar | 5 | 36 |  |  |  |  | YES |  | Henry County | YES | Mary (Beth) E Major | 2020-11-09 |  |  | 2020-11-09 |  |  |  | 2021-02-05
Greensville County Solar Project | RE0000093 | Permit - Active | Solar | 80 | 1125 | 0 |  | 0 | 646 | No | YES | Greensville County | No | Mary (Beth) E Major | 2018-10-10 |  |  | 2019-07-18 |  |  |  | 2019-10-15 |  |  | 2019-12-20 | 2020-12-01
Greenwood Solar I, LLC | RE0000059 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Culpeper County | No | Mary (Beth) E Major | 2017-07-20 |  | 2018-10-08
Greenwood Solar I, LLC | RE0000123 | Permit - Active | Solar | 100 | 1384 |  |  |  | 1000 | No | YES | Culpeper County | No | Mary (Beth) E Major | 2018-10-08 |  |  | 2020-07-28 |  |  |  | 2020-09-22
Halifax CSG Solar | RE0000255 | Permit - Active | Solar | 3.1 | 43 |  |  |  |  | YES |  | Halifax County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Halifax Solar, LLC | RE0000035 | NOI - Withdrawn | Solar | 15 | 125 | 0 |  | 0 | 0 | No | YES | Halifax County | No | Mary (Beth) E Major | 2017-02-08 |  | 2019-10-29
Harris Road Solar 1 Facility | RE0000251 | Permit - Active | Solar | 3 | 119 |  |  |  | 33 | YES | No | Lancaster County | No | Susan M Tripp | 2022-11-03 |  |  | 2022-11-03 |  |  |  | 2022-11-07
Harris Road Solar 2 Facility | RE0000252 | Permit - Active | Solar | 2 | 119 |  |  |  | 23 | YES |  | Lancaster County | No | Susan M Tripp | 2022-10-21 |  |  | 2022-11-03 |  |  |  | 2022-12-15
Haynesville Correctional Center | RE0000134 | Permit - Active | Solar | 0.6 | 136 |  |  |  | 5 | YES | No | Richmond County | No | Mary (Beth) E Major | 2018-04-19 | [6 empty] | 2018-06-11
HCE Amelia Solar I | RE0000159 | Permit - Active | Solar | 5 | 98 |  |  |  | 32 | YES | No | Amelia County | No | Mary (Beth) E Major | 2020-05-11 |  |  | 2020-05-11 |  |  |  | 2020-06-17
HCE Amelia Solar I, LLC | RE0000103 | NOI - Withdrawn | Solar | 10 | 60 | 0 |  | 0 | 0 | No | No | Amelia County | No | Mary (Beth) E Major | 2019-04-17 |  | 2020-05-06
HCE Amelia Solar II | RE0000166 | Permit - Active | Solar | 5 | 190 |  |  |  | 30 | YES | No | Amelia County | No | Mary (Beth) E Major | 2020-05-11 |  |  | 2020-05-11 |  |  |  | 2020-06-17
HCE Bustleburg Solar | RE0000178 | Permit - Active | Solar | 2.5 | 90 |  |  |  | 15 | YES |  | Rockbridge County | No | Mary (Beth) E Major | 2020-09-18 |  |  | 2020-09-18 |  |  |  | 2021-02-05
HCE Collier Solar | RE0000335 | NOI - Active | Solar | 7.5 | 160 |  |  |  |  | No |  | Wise County | No | Matthew A Snow | 2024-11-19
HCE Cropp Solar | RE0000336 | NOI - Active | Solar | 6.8 | 55 |  |  |  |  | No |  | Stafford County | No | Matthew A Snow | 2024-11-19
HCE Maddens Tavern Solar | RE0000337 | NOI - Active | Solar | 9.5 | 78 |  |  |  |  | No |  | Culpeper County | No | Matthew A Snow | 2024-11-19
HCE Millboro Springs Solar | RE0000160 | Permit - Active | Solar | 5 | 23 |  |  |  |  | YES | No | Bath County | No | Mary (Beth) E Major | 2020-05-11 |  |  | 2020-05-11 |  |  |  | 2020-06-17
HCE Moran Solar | RE0000168 | Permit - Active | Solar | 3 | 154 |  |  |  | 18 | YES | No | Prince Edward County | No | Mary (Beth) E Major | 2020-05-29 |  |  | 2020-05-29 |  |  |  | 2020-06-17
HCE Mountain Run Solar | RE0000338 | NOI - Active | Solar | 7.5 | 74 |  |  |  |  | No |  | Culpeper County | No | Matthew A Snow | 2024-11-19
HCE Powhatan Solar | RE0000165 | Permit - Active | Solar | 5 | 40 |  |  |  |  | YES | No | Powhatan County | No | Mary (Beth) E Major | 2020-05-11 |  |  | 2020-05-11 |  |  |  | 2020-06-17
HCE Reams Solar | RE0000179 | Permit - Active | Solar | 5 | 62 |  |  |  | 35 | YES |  | Dinwiddie County | No | Mary (Beth) E Major | 2020-11-30 |  |  | 2020-11-30 |  |  |  | 2021-02-05
HCE Red House Solar, LLC | RE0000164 | Permit - Active | Solar | 5 | 110 |  |  |  | 33 | YES | No | Charlotte County | No | Mary (Beth) E Major | 2020-05-11 |  |  | 2020-05-11 |  |  |  | 2020-06-17 |  |  | 2021-08-12
HCE Roark Mill Solar | RE0000161 | Permit - Active | Solar | 3 | 230 |  |  |  | 20 | YES | No | Pittsylvania County | No | Mary (Beth) E Major | 2020-05-18 |  |  | 2020-05-18 |  |  |  | 2020-06-17
HEC Acorn Solar Facility | RE0000210 | Permit - Active | Solar | 1.4 | 9 |  |  |  |  | YES |  | Harrisonburg City | No | Mary (Beth) E Major | 2021-11-30 |  |  | 2021-11-30 |  |  |  | 2022-01-21
Hecate Energy Cherrydale | RE0000003 | Permit - Active | Solar | 20 | 236 | 0 |  | 0 | 0 | No | No | Northampton County | No | Mary (Beth) E Major | 2015-10-13 |  |  | 2016-07-13 |  |  |  | 2016-08-15 |  |  | 2017-03-30 | 2017-10-25
Hecate Energy Clarke County, LLC | RE0000004 | Permit - Active | Solar | 20 | 235 | 0 |  | 0 | 0 | No | YES | Clarke County | No | Mary (Beth) E Major | 2015-10-13 |  |  | 2016-08-18 |  |  |  | 2016-09-22 |  |  | 2017-02-15 | 2017-07-26
Hemings Solar | RE0000195 | Permit - Active | Solar | 4.9 | 86 |  |  |  | 35 | YES |  | Richmond County | No | Mary (Beth) E Major | 2021-01-27 |  |  | 2021-03-08 |  |  |  | 2021-03-08
Hera Solar | RE0000328 | NOI - Active | Solar | 20 | 720 |  |  |  |  | No |  | Tazewell County | No | Amber K Foster | 2024-09-23
Hickory Solar 1 LLC | RE0000121 | NOI - Withdrawn | Solar | 20 | 90 |  |  |  |  | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2017-02-08 |  | 2018-08-02
Hickory Solar 2 LLC | RE0000122 | NOI - Withdrawn | Solar | 15 | 60 |  |  |  |  | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2017-02-08 |  | 2018-08-02
High Bridge Solar | RE0000321 | NOI - Active | Solar | 12 | 131 |  |  |  |  | No |  | Prince Edward County | No | Amber K Foster | 2024-06-26
Ho-Fel Solar | RE0000225 | Permit - Active | Solar | 40 | 350 |  |  |  |  | No | YES | Isle of Wight County | No | Susan M Tripp | 2022-03-30 |  |  | 2023-03-27 |  | 2023-05-23 | 2023-03-14 | 2023-06-08
Ho-Fel Solar Project | RE0000091 | NOI - Withdrawn | Solar | 39 | 292 | 0 |  | 0 | 0 | No | No | Isle of Wight County | No | Mary (Beth) E Major | 2018-10-02 |  | 2022-03-28
Hollyfield | RE0000049 | Permit - Active | Solar | 17 | 160 | 0 |  | 0 | 0 | No | No | King William County | YES | Mary (Beth) E Major | 2017-05-19 |  |  | 2017-08-15 |  |  |  | 2017-10-02 |  |  | 2017-10-10 | 2018-09-06
Hollyfield II Solar, LLC | RE0000040 | Permit - Active | Solar | 13 | 231 | 0 |  | 0 | 170 | No | YES | King William County | YES | Mary (Beth) E Major | 2017-03-03 |  |  | 2018-01-29 |  |  |  | 2018-03-29 |  |  | 2020-07-14 | 2021-07-22
Impact Power Solutions / Larry Davis Solar | RE0000271 | Permit - Active | Solar | 1.8 | 50 |  |  |  | 13 | YES | No | Buckingham County | No | Amber K Foster | 2023-02-03 |  |  | 2023-02-13 |  |  |  | 2023-02-17
Impact Power Solutions / NCN Properties 3 | RE0000272 | Permit - Active | Solar | 2 | 21 |  |  |  | 13 | YES | No | Buckingham County | No | Amber K Foster | 2023-02-03 |  |  | 2023-01-27 |  |  |  | 2023-02-17
Impact Power Solutions / Self 4 – Inez Smith | RE0000273 | Permit - Active | Solar | 4.5 | 64 |  |  |  | 27 | YES | No | Richmond County | No | Amber K Foster | 2023-01-27 |  |  | 2023-02-03 |  |  |  | 2023-02-17
Impact Power Solutions / Town of Gretna I | RE0000275 | Permit - Active | Solar | 1 | 138 |  |  |  | 5 | YES | No | Pittsylvania County | No | Amber K Foster | 2023-02-13 |  |  | 2023-02-10 |  |  |  | 2023-02-17
James Energy Center | RE0000319 | Permit - Active | Energy Storage | 20 | 3 |  |  |  |  | YES |  | Lynchburg City | No | Amber K Foster | 2024-06-25 |  |  | 2024-12-13 | 2024-12-16 |  |  | 2025-01-06
Jarratt Energy Facility | RE0000157 | Permit - Active | Solar | 49 | 500 |  |  |  |  | No | No | Greensville County | No | Susan M Tripp | 2020-03-18 |  |  | 2022-05-26 |  |  |  | 2022-08-24
Jouett Elementary School | RE0000188 | Permit - Active | Solar | 0.8 | 4 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2020-11-18 |  |  | 2021-02-02 |  |  |  | 2021-03-05
Kangaroo Solar, LLC | RE0000183 | NOI - Active | Solar | 14.5 | 137 |  |  |  |  | No |  | Campbell County | No | Mary (Beth) E Major | 2020-12-04
KDC Solar Kings Creek, LLC | RE0000130 | Permit - Active | Solar | 20 | 395 |  |  |  | 200 | YES | No | James City County | YES | Mary (Beth) E Major | 2019-10-31 |  |  | 2019-10-31 |  |  |  | 2019-11-05
Kentuck Solar, LLC | RE0000013 | Permit - Active | Solar | 6 | 77 | 0 |  | 0 | 0 | YES | No | Pittsylvania County | No | Mary (Beth) E Major | 2016-04-27 | [6 empty] | 2016-08-29
King William Solar, LLC | RE0000167 | Permit - Active | Solar | 1.5 | 4 |  |  |  |  | YES | No | King William County | No | Mary (Beth) E Major | 2020-03-04 |  |  | 2020-03-04 |  |  |  | 2020-06-10
Kinglet Solar | RE0000304 | Permit - Active | Solar | 5 | 172 |  |  |  | 40 | YES | No | Stafford County | No | Amber K Foster | 2023-11-21 |  |  | 2023-11-21 | 2023-11-22 |  |  | 2023-12-01
Knollwood Halifax Solar | RE0000277 | Permit - Active | Solar | 5 | 140 |  |  |  | 50 | YES | No | Halifax County | No | Amber K Foster | 2023-03-15 |  |  | 2023-03-15 |  |  |  | 2023-03-17
Koala Solar, LLC | RE0000182 | NOI - Active | Solar | 14.5 | 131 |  |  |  |  | No |  | Campbell County | No | Mary (Beth) E Major | 2020-12-04
Ladybug Solar, LLC | RE0000067 | NOI - Withdrawn | Solar | 65 | 478 | 0 |  | 0 | 0 | No | YES | Mecklenburg County | No | Mary (Beth) E Major | 2017-10-16 |  | 2019-07-10
Land of Promise Solar, LLC | RE0000323 | Permit - Active | Solar | 5 | 135 |  |  |  | 21 | YES |  | Chesapeake City | No | Matthew A Snow | 2024-07-15 |  |  | 2024-07-15 |  |  |  | 2024-07-16
Lily Pond Solar, LLC | RE0000105 | NOI - Withdrawn | Solar | 83 | 2000 | 0 |  | 0 | 0 | No | No | Dinwiddie County | No | Mary (Beth) E Major | 2019-05-15 |  | 2022-04-08
Loblolly Solar, LLC | RE0000086 | NOI - Active | Solar | 150 | 1384 | 0 |  | 0 | 0 | No | No | Surry County | No | Mary (Beth) E Major | 2018-09-07
Louisa County Middle School Solar Facility | RE0000192 | Permit - Active | Solar | 1.3 | 5 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2020-11-18 |  |  | 2021-02-02 |  |  |  | 2021-03-05
Maples Solar | RE0000231 | NOI - Active | Solar | 15 | 200 |  |  |  |  | No |  | Fauquier County | No | Susan M Tripp | 2022-05-27
Maplewood Solar | RE0000149 | Permit - Active | Solar | 120 | 1850 |  |  |  | 1556 | No | YES | Pittsylvania County | No | Mary (Beth) E Major | 2019-11-27 |  |  | 2020-03-16 |  |  |  | 2020-06-10 |  |  | 2020-07-20 | 2022-12-19
Maplewood Solar I, LLC | RE0000058 | NOI - Withdrawn | Solar | 120 | 1200 | 0 |  | 0 | 0 | No | YES | Pittsylvania County | No | Mary (Beth) E Major | 2017-07-20 |  | 2019-10-10
Martin Solar Center, LLC | RE0000140 | Permit - Active | Solar | 5 | 114 |  |  |  | 35 | YES | No | Fluvanna County | No | Mary (Beth) E Major | 2017-06-06 | [6 empty] | 2017-06-06 |  |  |  | 2017-12-01
Martin Trail Farm Solar | RE0000265 | Permit - Active | Solar | 5 | 40 |  |  |  |  | YES | No | Halifax County | No | Amber K Foster | 2022-11-29 |  |  | 2022-11-29 |  |  |  | 2022-12-08
Martinsville Solar, LLC | RE0000200 | Permit - Active | Solar | 8 | 55 |  |  |  |  | YES |  | Martinsville City | YES | Mary (Beth) E Major | 2021-04-12 | [6 empty] | 2021-06-03
Mechanicsville Solar, LLC | RE0000021 | Permit - Active | Solar | 25 | 250 | 0 |  | 0 | 0 | No | YES | Hanover County | No | Mary (Beth) E Major | 2016-09-12 |  |  | 2017-08-08 |  |  |  | 2017-09-26 | 2020-05-06 | 2020-05-18 | 2019-12-09 | 2020-06-10
Michaux Solar Center, LLC | RE0000199 | NOI - Withdrawn | Solar | 50 | 600 |  |  |  |  | No |  | Henry County | No | Mary (Beth) E Major | 2021-03-25 |  | 2023-04-06
Midway Solar, LLC | RE0000203 | Permit - Active | Solar | 8 | 136 |  |  |  | 80 | No | YES | Albemarle County | No | Amber K Foster | 2021-06-25 |  |  | 2022-11-28 |  | 2023-02-16 | 2021-11-03 | 2023-03-07
Mine & Hemmer Solar | RE0000239 | Permit - Active | Solar | 94 | 460 |  |  |  | 229 | No | YES | Louisa County | No | Susan M Tripp | 2022-08-05 |  |  | 2023-03-10 |  | 2023-04-12 | 2023-02-22 | 2023-06-01
Mineral Gap Data Center | RE0000220 | Permit - Active | Solar | 3 | 14 |  |  |  |  | YES | No | Wise County | YES | Mary (Beth) E Major | 2021-02-23 | [6 empty] | 2022-01-13
Monroe Solar | RE0000177 | Permit - Active | Solar | 2.2 | 62 |  |  |  | 35 | YES |  | Pittsylvania County | No | Mary (Beth) E Major | 2020-11-04 |  |  | 2020-11-04 |  |  |  | 2021-02-05
Montross Solar | RE0000075 | Permit - Active | Solar | 20 | 337 | 0 |  | 0 | 120 | No | YES | Westmoreland County | No | Mary (Beth) E Major | 2017-11-30 |  |  | 2018-02-16 |  |  |  | 2018-05-17 |  |  | 2018-07-20 | 2018-12-12
Moody Creek Solar, LLC | RE0000118 | Permit - Active | Solar | 150 | 1631 |  |  |  | 798 | No | YES | Charlotte County | No | Mary (Beth) E Major | 2019-10-21 |  |  | 2021-03-12 |  | 2021-04-14 |  | 2021-06-01
Moraticco Road Solar 1 | RE0000148 | NOI - Active | Solar | 20 | 50 |  |  |  |  | No | No | Lancaster County | No | Mary (Beth) E Major | 2019-12-02
Moseley Hermon Solar | RE0000311 | Permit - Active | Solar | 5 | 135 |  |  |  | 32 | YES |  | Chesterfield County | No | Amber K Foster | 2023-05-10 | 2024-12-03 |  | 2023-05-10 | 2024-02-22 |  |  | 2024-12-04
Moss Nuckols Elementary School | RE0000185 | Permit - Active | Solar | 0.8 | 4 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2020-11-18 |  |  | 2021-02-02 |  |  |  | 2021-03-05
Mount Nebo Solar Partners, LLC | RE0000101 | NOI - Active | Solar | 20 | 80 | 0 |  | 0 | 0 | No | No | Surry County | No | Mary (Beth) E Major | 2019-02-06
Mountain Pine Arvonia I & II | RE0000332 | NOI - Active | Solar | 80 | 1065 |  |  |  | 572 | No |  | Buckingham County | No | Matthew A Snow | 2024-10-18
Mt Jackson Solar I, LLC | RE0000044 | Permit - Active | Solar | 16 | 185 | 0 |  | 0 | 0 | No | YES | Shenandoah County | No | Mary (Beth) E Major | 2017-04-20 |  |  | 2017-12-28 | 2018-06-20 |  |  | 2018-07-17 |  |  |  | 2021-06-14
Mt. Jackson Solar II, LLC | RE0000096 | NOI - Active | Solar | 19 | 175 | 0 |  | 0 | 0 | No | No | Shenandoah County | No | Mary (Beth) E Major | 2018-11-09
Mt. Jackson Solar III, LLC | RE0000124 | NOI - Active | Solar | 16.2 | 130 |  |  |  |  | No | No | Shenandoah County | No | Mary (Beth) E Major | 2018-11-09
Muskie Solar | RE0000241 | Permit - Active | Solar | 4.9 | 398 |  |  |  | 40 | YES |  | Caroline County | No | Amber K Foster | 2022-07-21 |  |  | 2022-07-21 |  |  |  | 2022-09-09
Nansemond Solar | RE0000317 | Permit - Active | Solar | 5 | 40 |  |  |  | 36 | YES | No | Suffolk City | No | Amber K Foster | 2024-06-11 |  |  | 2024-06-11 |  |  |  | 2024-06-16
Naples Solar, LLC | RE0000181 | NOI - Withdrawn | Solar | 14 | 126 |  |  |  |  | No |  | Orange County | No | Mary (Beth) E Major | 2020-12-04 |  | 2022-04-11
NASA Wallops Flight Facility - Main Base | RE0000141 | Permit - Active | Solar | 3.5 | 26 |  |  |  |  | YES | No | Accomack County | No | Mary (Beth) E Major | 2018-12-03 | [6 empty] | 2018-12-17
NASA Wallops Flight Facility Phase 3B | RE0000163 | Permit - Active | Solar | 4.9 | 26 |  |  |  |  | YES | No | Accomack County | No | Mary (Beth) E Major | 2020-02-05 | [6 empty] | 2020-02-21
North Branch Solar | RE0000339 | Permit - Active | Solar | 3 | 147 |  |  |  | 40 | YES | No | Prince Edward County | No | Amber K Foster | 2024-11-26 |  |  | 2024-11-07 | 2024-11-26 |  |  | 2024-12-05
North Ridge Culpeper Solar | RE0000266 | NOI - Active | Solar | 26 | 345 |  |  |  |  | No |  | Culpeper County | No | Susan M Tripp | 2022-12-12
North Ridge Powhatan Solar LLC | RE0000174 | Permit - Terminated without Cause | Solar | 20 | 197 |  |  |  |  | No | No | Powhatan County | No | Mary (Beth) E Major | 2020-09-14 |  |  | 2021-07-28 |  |  |  | 2021-11-30
Nuby Run Solar | RE0000288 | Permit - Active | Solar | 2 | 178 |  |  |  | 27 | YES | No | Isle of Wight County | No | Amber K Foster | 2023-06-29 |  |  | 2023-06-29 |  |  |  | 2023-07-11 |  |  | 2023-06-28
Oral Oaks Road Solar | RE0000333 | NOI - Active | Solar | 12 | 128 |  |  |  |  | No |  | Lunenburg County | No | Matthew A Snow | 2024-10-16 | [5 empty] | 2024-11-18
Otter Creek Solar, LLC | RE0000055 | Permit - Terminated without Cause | Solar | 60 | 685 | 0 |  | 0 | 0 | No | No | Mecklenburg County | No | Mary (Beth) E Major | 2017-06-14 |  |  | 2019-08-12 |  |  |  | 2019-10-24
Palmer Solar Center, LLC | RE0000142 | NOI - Active | Solar | 5 | 41 |  |  |  |  | YES | No | Fluvanna County | No | Mary (Beth) E Major | 2017-06-06
Pamplin Solar, LLC | RE0000038 | Permit - Active | Solar | 15.7 | 112 | 0 |  | 0 | 82 | No | YES | Appomattox County | No | Mary (Beth) E Major | 2017-02-08 |  |  | 2018-06-15 |  |  |  | 2018-08-28 |  |  |  | 2020-07-13
Partridge Creek Solar | RE0000285 | NOI - Active | Solar | 10 | 141 |  |  |  | 90 | No |  | Amherst County | No | Amber K Foster | 2023-05-18
Peppertown Road Solar | RE0000295 | Permit - Active | Solar | 5 | 32 |  |  |  | 19 | YES |  | Hanover County | No | Amber K Foster | 2023-09-06 |  |  | 2023-08-31 | 2023-09-06 |  |  | 2023-10-11
Pigeon Run Solar, LLC | RE0000136 | Permit - Active | Solar | 60 | 612 |  |  |  | 296 | No | YES | Campbell County | No | Mary (Beth) E Major | 2019-11-19 |  |  | 2021-04-26 |  |  |  | 2021-08-04
Piney Creek Solar | RE0000087 | NOI - Withdrawn | Solar | 80 | 700 | 0 |  | 0 | 0 | No | No | Halifax County | No | Mary (Beth) E Major | 2018-09-07 |  | 2021-03-01
Piney River Solar | RE0000282 | NOI - Active | Solar | 50 | 431 |  |  |  | 180 | No |  | Amherst County | No | Amber K Foster | 2023-04-13
Pittsylvania CSG Solar | RE0000258 | Permit - Active | Solar | 3.8 | 52 |  |  |  | 14 | YES | No | Pittsylvania County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Pleasant Hill Solar | RE0000098 | Permit - Active | Solar | 20 | 208 | 0 |  | 0 | 180 | No | No | Suffolk City | No | Mary (Beth) E Major | 2018-11-20 |  |  | 2020-11-13 |  |  | 2020-10-13 | 2021-02-05
Pocaty River Solar, LLC | RE0000324 | Permit - Active | Solar | 2 | 27 |  |  |  | 9 | YES |  | Chesapeake City | No | Matthew A Snow | 2024-07-15 |  |  | 2024-07-15 |  |  |  | 2024-07-17
Port Conway Solar, LLC | RE0000053 | NOI - Active | Solar | 20 | 250 | 0 |  | 0 | 0 | No | No | King George County | No | Mary (Beth) E Major | 2017-06-07
Powell Creek Solar | RE0000264 | Permit - Active | Solar | 5 | 631 |  |  |  | 47 | YES | No | Prince George County | No | Amber K Foster | 2022-11-29 |  |  | 2022-11-29 |  |  |  | 2022-12-08
Powells Creek Farm Solar, LLC | RE0000045 | Permit - Active | Solar | 70 | 710 | 0 |  | 0 | 502 | No | YES | Halifax County | No | Mary (Beth) E Major | 2017-04-21 |  |  | 2019-02-13 |  |  |  | 2019-05-02 |  |  | 2022-08-16
Powhatan Solar I, LLC | RE0000143 | Permit - Terminated without Cause | Solar | 18 | 225 |  |  |  |  | No | YES | Powhatan County | No | Mary (Beth) E Major | 2019-11-21 |  |  | 2020-08-13 |  | 2020-10-20 |  | 2021-04-02
Prairie Solar | RE0000291 | Permit - Active | Solar | 20 | 433 |  |  |  | 201 | No | YES | Isle of Wight County | No | Amber K Foster | 2023-06-30 |  |  | 2023-09-12 |  |  |  | 2023-10-27 |  |  | 2025-02-24
Prince Edward CSG Solar | RE0000259 | Permit - Active | Solar | 4 | 85 |  |  |  |  | YES | No | Prince Edward County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Prince Edward Solar 1 | RE0000276 | Permit - Active | Solar | 5 | 86 |  |  |  | 20 | YES | No | Prince Edward County | No | Amber K Foster | 2023-02-20 |  |  | 2023-02-20 |  |  |  | 2023-03-02
Prince Edward Solar Farm | RE0000246 | Application - In Review | Solar | 25 | 304 |  |  |  | 194 | No | No | Prince Edward County | No | Matthew A Snow | 2022-10-26 |  |  | 2025-01-31 |  |  | 2024-11-06
Prospect Power | RE0000312 | Permit - Active | Energy Storage | 150 | 25 |  |  |  |  | No | YES | Rockingham County | No | Amber K Foster | 2024-04-10 |  |  | 2024-09-10 |  | 2024-10-18 | 2024-08-27 | 2024-11-08
Pulaski I Solar | RE0000212 | Permit - Active | Solar | 150 | 1664 |  |  |  | 981 | No | YES | Pulaski County | No | Amber K Foster | 2021-12-06 |  |  | 2023-02-16 | 2023-04-25 | 2023-12-14 | 2022-10-18 | 2024-01-16
Puller Solar | RE0000060 | Permit - Active | Solar | 15 | 201 | 0 |  | 0 | 170 | No | YES | Middlesex County | No | Mary (Beth) E Major | 2017-07-21 |  |  | 2017-09-13 |  |  |  | 2017-12-12 |  |  | 2018-03-16 | 2018-12-05
Pumpkinseed Solar | RE0000054 | Permit - Active | Solar | 60 | 836 | 0 |  | 0 | 381 | No | No | Greensville County | No | Mary (Beth) E Major | 2017-06-14 | 2019-05-08 |  | 2019-10-07 |  |  |  | 2019-12-17 |  |  | 2020-12-02 | 2022-09-29
Quarry Energy Center | RE0000320 | NOI - Active | Energy Storage | 20 | 3 |  |  |  |  | YES |  | Lynchburg City | No | Amber K Foster | 2024-06-25
Randolf Solar | RE0000190 | Permit - Active | Solar | 3.2 | 91 |  |  |  | 35 | YES |  | Shenandoah County | No | Mary (Beth) E Major | 2021-01-27 |  |  | 2021-03-08 |  |  |  | 2021-03-08 |  |  | 2023-03-06
Rappahannock Solar, LLC | RE0000147 | Permit - Active | Solar | 1.5 | 184 |  |  |  | 17 | YES | No | Lancaster County | No | Mary (Beth) E Major | 2019-07-09 | [6 empty] | 2019-07-09 |  |  |  | 2021-11-01
Red Brick Solar | RE0000233 | Permit - Active | Solar | 130 | 1938 |  |  |  | 1309 | No | YES | Lunenburg County | No | Susan M Tripp | 2022-06-15 |  |  | 2022-10-25 |  | 2022-10-28 | 2022-09-07 | 2023-03-03
Redbud Run Solar Project | RE0000209 | Permit - Terminated without Cause | Solar | 30 | 263 |  |  |  | 150 | No | YES | Frederick County | No | Amber K Foster | 2021-10-21 |  |  | 2022-09-26 | 2022-12-22 | 2023-04-12 | 2022-09-06 | 2023-05-01
Reed Road Solar 1 | RE0000330 | Permit - Active | Solar | 4 | 26 |  |  |  | 19 | YES | No | Roanoke County | No | Amber K Foster | 2024-09-27 |  |  | 2024-09-27 |  |  |  | 2024-09-30
RER Hopewell Battery Energy Storage | RE0000294 | NOI - Active | Energy Storage | 40 | 1 |  |  |  |  | YES | No | Hopewell City | YES | Amber K Foster | 2023-08-15
Reservoir Solar LLC, | RE0000062 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Louisa County | No | Mary (Beth) E Major | 2017-07-25 |  | 2017-10-31
Richmond Road Solar | RE0000344 | Permit - Active | Solar | 5 | 61 |  |  |  | 134 | YES | No | James City County | No | Amber K Foster | 2024-12-30 |  |  | 2024-12-30 |  |  |  | 2025-01-02
Rivanna Solar, LLC | RE0000108 | Permit - Active | Solar | 12.5 | 150 | 0 |  | 0 | 71 | No | No | Albemarle County | No | Mary (Beth) E Major | 2019-06-19 |  |  | 2019-10-16 |  |  |  | 2020-01-16
River Trail Solar | RE0000219 | Permit - Active | Solar | 20 | 390 |  |  |  | 169 | No | YES | Carroll County | No | Amber K Foster | 2021-12-10 |  |  | 2022-12-19 |  | 2023-03-13 | 2022-12-07 | 2023-04-25 | 2023-06-09 | 2023-09-22 | 2024-01-22
Riverstone Solar | RE0000211 | Permit - Active | Solar | 149.5 | 1992 |  |  |  | 1819 | No | YES | Buckingham County | No | Susan M Tripp | 2021-11-29 |  |  | 2022-07-28 |  | 2022-10-25 | 2022-06-07 | 2022-11-29
Rives Road Solar, LLC | RE0000037 | Permit - Active | Solar | 19.7 | 147 | 0 |  | 0 | 0 | No | No | Prince George County | No | Mary (Beth) E Major | 2017-02-08 |  |  | 2018-04-11 | 2018-09-18 | 2019-01-08 |  | 2019-01-15 |  |  |  | 2020-06-01
Rochambeau Solar, LLC | RE0000114 | NOI - Withdrawn | Solar | 19.9 | 192 | 0 |  | 0 | 0 | No | No | James City County | No | Mary (Beth) E Major | 2019-09-11 |  | 2019-12-20
Rochambeau Solar, LLC | RE0000150 | Permit - Active | Solar | 19.9 | 282 |  |  |  | 192 | No | YES | James City County | No | Mary (Beth) E Major | 2020-01-03 |  |  | 2020-03-13 |  |  | 2020-02-27 | 2020-05-12 |  |  | 2021-04-05 | 2021-12-23
Rocky Forge Wind, LLC | RE0000002 | Permit - Active | Wind | 80 | 200 | 0 |  | 0 | 0 | No | YES | Botetourt County | No | Mary (Beth) E Major | 2015-06-25 |  |  | 2016-05-03 |  |  |  | 2017-03-02 | 2020-08-25 | 2020-10-16 | 2021-03-18
Route 360 Solar | RE0000263 | Permit - Active | Solar | 5 | 40 |  |  |  |  | YES | No | Halifax County | No | Amber K Foster | 2022-11-29 |  |  | 2022-11-29 |  |  |  | 2022-12-08
Rye Cove Solar 1 | RE0000345 | Permit - Active | Solar | 4 | 197 |  |  |  | 35 | YES | No | Scott County | No | Amber K Foster | 2025-02-06 |  |  | 2025-02-06 |  |  |  | 2025-02-10
Sadler Solar | RE0000100 | NOI - Withdrawn | Solar | 102 | 1490 | 0 |  | 0 | 0 | No | No | Greensville County | No | Mary (Beth) E Major | 2019-02-06 |  | 2020-06-01
Sandale Solar | RE0000290 | Permit - Active | Solar | 3 | 58 |  |  |  | 23 | YES | No | Lancaster County | No | Amber K Foster | 2023-06-20 | [6 empty] | 2023-07-11
SB Solar, LLC | RE0000068 | NOI - Active | Solar | 10 | 185 | 0 |  | 0 | 0 | No | No | Halifax County | No | Mary (Beth) E Major | 2017-10-16
Scott II Solar LLC | RE0000018 | Permit - Active | Solar | 20 | 720 | 0 |  | 0 | 230 | No | No | Powhatan County | No | Mary (Beth) E Major | 2016-06-09 |  |  | 2016-10-11 |  |  |  | 2016-12-08 |  |  | 2017-04-25 | 2017-11-29
Scout Energy Storage Facility | RE0000237 | Permit - Active | Energy Storage | 80 | 10 |  |  |  |  | YES |  | Accomack County | No | Amber K Foster | 2022-08-05 |  |  | 2022-10-06 |  |  |  | 2023-01-03
Sedge Hill Solar | RE0000318 | NOI - Active | Solar | 80 | 1130 |  |  |  | 812 | No |  | Halifax County | No | Amber K Foster | 2024-06-26
Self I Solar LLC | RE0000268 | Permit - Active | Solar | 5 | 49 |  |  |  | 34 | YES | No | Richmond County | No | Amber K Foster | 2023-01-11 |  |  | 2023-01-12 |  |  |  | 2023-01-12
Seven Bridges Solar | RE0000144 | NOI - Active | Solar | 116 | 2550 |  |  |  |  | No | No | Mecklenburg County | No | Amber K Foster | 2019-11-26
Shad Solar | RE0000236 | Permit - Active | Solar | 4.9 | 44 |  |  |  | 38 | YES |  | Caroline County | No | Amber K Foster | 2022-07-21 |  |  | 2022-07-21 |  |  |  | 2022-09-09
Shifting Sands Solar | RE0000234 | Permit - Active | Solar | 18.8 | 251 |  |  |  | 152 | No | YES | Henry County | No | Susan M Tripp | 2022-07-15 |  |  | 2023-03-03 |  |  | 2023-02-13 | 2023-05-16 |  |  | 2024-01-22
Shockoe Solar, LLC | RE0000173 | Permit - Active | Solar | 60 | 903 |  |  |  | 290 | No | YES | Pittsylvania County | No | Mary (Beth) E Major | 2020-09-09 |  |  | 2021-06-23 |  |  |  | 2021-10-21
Sigora Solar | RE0000051 | NOI - Active | Solar | 40 | 126 | 0 |  | 0 | 0 | No | No | Wythe County | No | Mary (Beth) E Major | 2017-05-24
Smithfield Solar Farm | RE0000009 | NOI - Withdrawn | Solar | 14 | 122 | 0 |  | 0 | 0 | No | No | Isle of Wight County | No | Mary (Beth) E Major | 2016-03-29 |  | 2024-10-30
Sol Leatherwood Solar, LLC | RE0000079 | Permit - Active | Solar | 20 | 322 | 0 |  | 0 | 0 | No | YES | Henry County | No | Mary (Beth) E Major | 2018-05-21 |  |  | 2018-10-18 |  |  |  | 2018-12-17 |  |  | 2021-01-08 | 2021-08-09
Sol Madison Solar, LLC | RE0000081 | Permit - Active | Solar | 62.5 | 355 | 0 |  | 0 | 0 | No | YES | Orange County | No | Mary (Beth) E Major | 2018-06-18 |  |  | 2019-02-05 |  |  |  | 2019-04-23 | 2020-04-21 | 2020-06-10 | 2021-07-26 | 2024-09-13
Solar Access Development Group, LLC | RE0000020 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Culpeper County | No | Mary (Beth) E Major | 2016-08-15 |  | 2017-02-09
Solar Star Buchanan 2 | RE0000300 | Permit - Active | Solar | 4.5 | 405 |  |  |  | 23 | YES | No | Botetourt County | No | Amber K Foster | 2023-10-20 |  |  | 2023-10-20 | 2023-10-25 |  |  | 2023-11-14
Solar Star Petersburg 1 | RE0000274 | Permit - Active | Solar | 4.8 | 22 |  |  |  | 20 | YES |  | Petersburg City | No | Susan M Tripp | 2023-02-02 |  |  | 2023-02-02 |  |  |  | 2023-05-09
Solar VA 2019 LLC | RE0000198 | Permit - Active | Solar | 18 | 125 |  |  |  | 55 | No | YES | Westmoreland County | No | Susan M Tripp | 2021-03-19 |  |  | 2021-07-12 |  | 2022-01-14 |  | 2022-06-27
Solidago, LLC | RE0000047 | NOI - Withdrawn | Solar | 20 | 160 | 0 |  | 0 | 0 | No | No | Isle of Wight County | No | Mary (Beth) E Major | 2017-04-21 |  | 2021-05-05
SolUnesco Jefferson | RE0000026 | NOI - Withdrawn | Solar | 11 | 71 | 0 |  | 0 | 0 | No | YES | Albemarle County | No | Mary (Beth) E Major | 2016-11-04 |  | 2019-06-19
SolUnesco Leatherwood | RE0000024 | NOI - Withdrawn | Solar | 20 | 120 | 0 |  | 0 | 0 | No | YES | Henry County | No | Mary (Beth) E Major | 2016-11-04 |  | 2018-05-21
SolUnesco Locust Grove | RE0000023 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Orange County | No | Mary (Beth) E Major | 2016-11-04 |  | 2018-06-18
SolUnesco Racehorse | RE0000025 | NOI - Active | Solar | 15 | 90 | 0 |  | 0 | 0 | No | No | Caroline County | No | Mary (Beth) E Major | 2016-11-04
South Boston G Solar | RE0000314 | Permit - Active | Solar | 5 | 125 |  |  |  | 39 | YES |  | Halifax County | No | Amber K Foster | 2024-05-28 |  |  | 2024-05-28 |  |  |  | 2024-06-06
South Boston I Solar | RE0000302 | Permit - Active | Solar | 5 | 48 |  |  |  | 38 | YES | No | South Boston City | No | Amber K Foster | 2023-10-27 |  |  | 2023-10-27 | 2023-11-02 |  |  | 2023-11-09
Southampton Solar, LLC | RE0000015 | Permit - Active | Solar | 100 | 1200 | 0 |  | 0 | 0 | No | YES | Southampton County | No | Mary (Beth) E Major | 2016-05-16 |  |  | 2016-12-19 |  |  |  | 2017-01-24 |  |  | 2017-03-08 | 2017-11-26
Spout Springs Solar LLC | RE0000036 | NOI - Active | Solar | 20 | 85 | 0 |  | 0 | 0 | No | No | Appomattox County | No | Mary (Beth) E Major | 2017-02-08
Spring Grove Solar II, LLC | RE0000074 | Permit - Active | Solar | 150 | 1650 | 0 |  | 0 | 0 | No | No | Surry County | No | Mary (Beth) E Major | 2020-09-08 |  |  | 2020-12-11 |  |  |  | 2021-03-04
Spring Grove Solar I, LLC | RE0000073 | NOI - Withdrawn | Solar | 150 | 1338 | 0 |  | 0 | 0 | No | No | Surry County | No | Mary (Beth) E Major | 2017-11-09 |  | 2020-06-01
Spring Grove Solar, LLC | RE0000042 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Surry County | No | Mary (Beth) E Major | 2017-03-14 |  | 2017-11-09
Springfield Farm Solar | RE0000283 | NOI - Active | Solar | 80 | 326 |  |  |  | 938 | No |  | Hanover County | No | Susan M Tripp | 2023-04-24
Stagecoach Solar, LLC | RE0000064 | NOI - Active | Solar | 15 | 318 | 0 |  | 0 | 0 | No | No | Halifax County | No | Mary (Beth) E Major | 2017-08-31
Staunton Community Solar Project | RE0000293 | Permit - Active | Solar | 5 | 95 |  |  |  | 25 | YES | No | Staunton City | No | Amber K Foster | 2023-07-27 |  |  | 2023-07-27 |  |  |  | 2023-07-28
Staunton Solar | RE0000202 | NOI - Active | Solar | 47 | 300 |  |  |  | 65 | No |  | Halifax County | No | Mary (Beth) E Major | 2021-07-01
Staunton Utility Solar Project | RE0000292 | NOI - Active | Solar | 11 | 95 |  |  |  | 65 | No |  | Staunton City | No | Amber K Foster | 2023-07-25 | [5 empty] | 2025-03-13
Stratford Solar Center, LLC | RE0000153 | NOI - Withdrawn | Solar | 15 | 150 |  |  |  |  | No | No | Suffolk City | No | Mary (Beth) E Major | 2020-02-18 |  | 2020-09-22
Stratford Solar Center, LLC | RE0000175 | Permit - Active | Solar | 15 | 154 |  |  |  | 109 | No | YES | Suffolk City | No | Mary (Beth) E Major | 2020-09-24 |  |  | 2021-06-04 |  |  | 2021-04-04 | 2021-09-15 |  |  | 2022-01-31 | 2022-12-01
STS J. Hodges, LLC (Middlesex ES and MS) | RE0000128 | Permit - Active | Solar | 1 | 4 |  |  |  |  | YES | No | Middlesex County | No | Mary (Beth) E Major | 2019-08-08 |  |  | 2019-08-08 |  |  |  | 2019-11-18
STS Joan Bosch, LLC (Cople ES) | RE0000129 | Permit - Active | Solar | 0.7 | 3 |  |  |  |  | YES | No | Westmoreland County | No | Mary (Beth) E Major | 2019-08-08 |  |  | 2021-04-05 |  |  |  | 2020-06-30
Suffolk CSG Solar | RE0000257 | Permit - Active | Solar | 4 | 21 |  |  |  |  | YES | No | Suffolk City | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Sun Ridge Solar | RE0000238 | NOI - Withdrawn | Solar | 50 | 564 |  |  |  |  | No |  | Rockingham County | YES | Susan M Tripp | 2022-08-15 |  | 2023-05-09
Sun Ridge Solar | RE0000286 | Permit - Active | Solar | 50 | 564 |  |  |  | 236 | No | YES | Rockingham County | No | Amber K Foster | 2023-05-08 |  |  | 2023-08-16 |  |  |  | 2023-11-08 |  |  | 2024-02-02
Sunfish Solar | RE0000306 | NOI - Active | Solar | 80 | 932 |  |  |  | 588 | No |  | Orange County | No | Amber K Foster | 2024-01-19
Sunny Rock Solar Project | RE0000278 | Permit - Active | Solar | 20 | 180 |  |  |  | 145 | No | YES | Henry County | No | Amber K Foster | 2023-03-07 |  |  | 2023-08-22 |  |  |  | 2023-11-20 |  |  | 2024-02-19
Sunnybrook Farm Solar, LLC | RE0000030 | Permit - Active | Solar | 51 | 352 | 0 |  | 0 | 242 | No | YES | Halifax County | No | Mary (Beth) E Major | 2016-12-09 |  |  | 2018-07-09 |  | 2018-09-21 |  | 2018-09-25 |  |  | 2022-01-27 | 2022-12-01
SunPower Corporation, James City | RE0000027 | NOI - Active | Solar | 35 | 225 | 0 |  | 0 | 0 | No | No | James City County | No | Mary (Beth) E Major | 2016-10-25
SunPower Corporation, Southampton | RE0000022 | NOI - Active | Solar | 91 | 525 | 0 |  | 0 | 0 | No | No | Southampton County | No | Mary (Beth) E Major | 2016-10-18
SunPower Garden Fresh Produce | RE0000206 | NOI - Active | Solar | 6.4 | 58 |  |  |  |  | No |  | Rockingham County | No | Mary (Beth) E Major | 2021-09-30
SunTec Solar ESVA One, LLC | RE0000008 | NOI - Active | Solar | 80 | 500 | 0 |  | 0 | 0 | No | No | Accomack County | No | Mary (Beth) E Major | 2016-03-19
Surry Solar Center, LLC | RE0000223 | NOI - Active | Solar | 20 | 225 |  |  |  |  | No |  | Surry County | No | Susan M Tripp | 2022-03-31
Sussex Drive Solar | RE0000017 | Permit - Active | Solar | 20 | 371 | 0 |  | 0 | 250 | No | No | Sussex County | No | Mary (Beth) E Major | 2016-06-09 |  |  | 2016-11-21 |  |  |  | 2017-01-12 |  |  | 2017-04-27 | 2017-11-30
Sweet Spring Solar | RE0000289 | Permit - Active | Solar | 1 | 116 |  |  |  | 19 | YES | No | Orange County | No | Amber K Foster | 2023-06-20 | [6 empty] | 2023-07-11
Sweet Sue Solar LLC | RE0000155 | NOI - Withdrawn | Solar | 77 | 576 |  |  |  |  | No | No | King William County | No | Mary (Beth) E Major | 2020-03-12 |  | 2021-11-22
Sweetspire, LLC | RE0000046 | NOI - Active | Solar | 20 | 165 | 0 |  | 0 | 0 | No | No | Hanover County | No | Mary (Beth) E Major | 2017-04-21
Sycamore Solar I, LLC | RE0000057 | NOI - Withdrawn | Solar | 42 | 420 | 0 |  | 0 | 0 | No | No | Pittsylvania County | No | Mary (Beth) E Major | 2017-07-20 |  | 2020-07-28
Sydnor Solar Farm | RE0000033 | Permit - Active | Solar | 3 | 50 | 0 |  | 0 | 20 | YES | No | Mecklenburg County | No | Mary (Beth) E Major | 2017-02-06
Tasley Energy Storage | RE0000342 | NOI - Active | Energy Storage | 10 | 1 |  |  |  |  | YES |  | Accomack County | No | Matthew A Snow | 2024-12-02
The Louisa County HIgh School Solar Facility | RE0000191 | Permit - Active | Solar | 1.8 | 7 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2020-11-18 |  |  | 2021-02-02 |  |  |  | 2021-03-05
Thomas Jefferson Elementary School Solar Facility | RE0000216 | Permit - Active | Solar | 0.5 | 7 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2021-10-27 | [6 empty] | 2021-10-27
Town of Gretna II | RE0000242 | Permit - Active | Solar | 4 | 63 |  |  |  | 24 | YES |  | Pittsylvania County | No | Susan M Tripp | 2022-08-31 |  |  | 2023-02-03 |  |  |  | 2023-02-17
TPE Irish Road Solar, LLC | RE0000127 | Permit - Active | Solar | 5 | 171 |  |  |  |  | YES | No | Danville City | No | Mary (Beth) E Major | 2019-04-04 | [6 empty] | 2019-05-07
TPE Pamplin2 Solar | RE0000078 | NOI - Active | Solar | 16 | 309 | 0 |  | 0 | 0 | No | No | Prince Edward County | No | Mary (Beth) E Major | 2018-01-22
Trevilians Elementary School | RE0000189 | Permit - Active | Solar | 0.6 | 3 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2020-11-18 |  |  | 2021-02-02 |  |  |  | 2021-03-05
Turkey Solar, LLC | RE0000184 | NOI - Active | Solar | 14 | 141 |  |  |  |  | No |  | Louisa County | No | Mary (Beth) E Major | 2020-12-04
Turner Solar, LLC | RE0000071 | Permit - Active | Solar | 20 | 581 | 0 |  | 0 | 463 | No | No | Henrico County | No | Mary (Beth) E Major | 2017-10-31 |  |  | 2018-11-29 | 2019-04-18 | 2019-05-28 |  | 2019-07-10
TWE Chesapeake Solar Project, LLC | RE0000012 | NOI - Withdrawn | Solar | 15 | 175 | 0 |  | 0 | 0 | No | No | Chesapeake City | No | Mary (Beth) E Major | 2016-03-31 |  | 2019-08-15
TWE Myrtle Solar Project, LLC | RE0000011 | Permit - Active | Solar | 15 | 135 | 0 |  | 0 | 110 | No | YES | Suffolk City | No | Mary (Beth) E Major | 2016-03-31 |  |  | 2018-02-12 |  |  |  | 2018-05-15 | 2020-01-15 | 2020-04-10 | 2020-01-29 | 2020-06-18
Twittys Creek Solar, LLC | RE0000019 | Permit - Active | Solar | 15 | 100 | 0 |  | 0 | 91 | No | No | Charlotte County | No | Mary (Beth) E Major | 2016-06-16 |  |  | 2017-10-19 |  |  |  | 2017-12-05 |  |  | 2020-06-12 | 2020-12-01
Two Oaks Solar | RE0000215 | Permit - Active | Solar | 118 | 1234 |  |  |  | 917 | No | YES | Louisa County | No | Amber K Foster | 2021-11-30 |  |  | 2024-03-11 | 2024-03-14 |  | 2024-02-28 | 2024-04-25
VA Cox Cartersville (Ampthill Rd) Solar Project | RE0000226 | Permit - Active | Solar | 16 | 86 |  |  |  | 80 | No | YES | Cumberland County | No | Susan M Tripp | 2022-04-22 |  |  | 2022-06-29 |  | 2022-09-19 | 2022-05-26 | 2022-11-23
VA Sinai Solar | RE0000284 | NOI - Active | Solar | 9.9 | 100 |  |  |  |  | No |  | Halifax County | No | Amber K Foster | 2023-04-12
Volvo Group North America LLC - NRV Plant | RE0000135 | Permit - Active | Wind | 4 | [5 empty] | YES | No | Pulaski County | No | Mary (Beth) E Major | 2013-09-10 | [6 empty] | 2013-09-16
VSF Solar 1, LLC | RE0000085 | NOI - Active | Solar | 20 | 114 | 0 |  | 0 | 0 | No | No | Westmoreland County | No | Mary (Beth) E Major | 2018-08-16
VSF Solar 2, LLC | RE0000099 | NOI - Active | Solar | 11 | 100 | 0 |  | 0 | 0 | No | No | Westmoreland County | No | Mary (Beth) E Major | 2018-11-21
Waller Solar | RE0000204 | Permit - Active | Solar | 131 | 2764 |  |  |  | 1200 | No | YES | Lancaster County | No | Mary (Beth) E Major | 2021-06-07 |  |  | 2023-01-06 |  | 2023-03-22 | 2022-12-14 | 2023-03-27
Walnut Solar I, LLC | RE0000056 | NOI - Withdrawn | Solar | 150 | 1800 | 0 |  | 0 | 0 | No | No | King and Queen County | No | Mary (Beth) E Major | 2017-07-20 |  | 2021-08-09
Warm Run Solar | RE0000343 | Permit - Active | Solar | 3 | 35 |  |  |  |  | YES |  | Rockbridge County | No | Matthew A Snow | 2024-12-16 |  |  | 2024-12-16 |  |  |  | 2024-12-19
Water Strider Solar, LLC | RE0000069 | Permit - Active | Solar | 80 | 1196 | 0 |  | 0 | 1042 | No | YES | Halifax County | No | Mary (Beth) E Major | 2017-10-16 |  |  | 2018-10-25 |  |  |  | 2019-04-30 |  |  | 2020-04-08 | 2021-05-15
Waterloo Solar | RE0000229 | NOI - Active | Solar | 20 | 234 |  |  |  | 125 | No |  | Prince William County | No | Amber K Foster | 2023-05-22 | 2023-05-22 |  |  |  |  | 2024-11-05
Watlington Solar, LLC | RE0000169 | Permit - Active | Solar | 20 | 220 |  |  |  | 140 | No | No | Halifax County | No | Mary (Beth) E Major | 2020-06-17 |  |  | 2021-01-06 |  |  |  | 2021-03-17
Waverly I Solar | RE0000222 | Permit - Active | Solar | 50 | 2992 |  |  |  | 1177 | No | YES | Sussex County | No | Susan M Tripp | 2022-03-28 |  |  | 2022-06-27 |  |  | 2022-06-14 | 2022-10-05 |  |  | 2023-06-01 | 2024-03-14
Waverly II Solar | RE0000228 | Permit - Active | Solar | 68 | 1700 |  |  |  | 438 | No | YES | Sussex County | No | Susan M Tripp | 2022-04-25 |  |  | 2022-12-05 |  | 2023-02-16 | 2022-11-16 | 2023-03-03 |  |  | 2023-06-07 | 2024-03-14
Waverly Solar, LLC | RE0000082 | NOI - Withdrawn | Solar | 118 | 2000 | 0 |  | 0 | 0 | No | No | Sussex County | No | Mary (Beth) E Major | 2018-07-02 |  | 2022-03-18
Wayne Ave Solar 2 | RE0000310 | Permit - Active | Solar | 3 | 37 |  |  |  | 23 | YES | No | Augusta County | No | Amber K Foster | 2024-02-20 |  |  | 2024-02-14 | 2024-02-16 |  |  | 2024-02-23
Wayne Ave Solar Facility | RE0000247 | Permit - Active | Solar | 3 | 80 |  |  |  | 25 | YES |  | Augusta County | No | Susan M Tripp | 2022-11-03 |  |  | 2022-11-03 |  |  |  | 2022-11-03
Waynesboro Bridge Solar | RE0000261 | Permit - Active | Solar | 5 | 90 |  |  |  | 40 | YES | No | Augusta County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Westmoreland County Solar Project | RE0000092 | Permit - Active | Solar | 20 | 161 | 0 |  | 0 | 100 | No | No | Westmoreland County | No | Mary (Beth) E Major | 2018-09-21 |  |  | 2019-11-04 |  |  |  | 2020-01-28 |  |  |  | 2021-10-01
Westmoreland CSG 1 | RE0000279 | Permit - Active | Solar | 5 | 80 |  |  |  | 22 | YES | No | Westmoreland County | No | Amber K Foster | 2023-03-17 |  |  | 2023-03-17 |  |  |  | 2023-03-27
Westmoreland Solar, LLC | RE0000052 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Westmoreland County | No | Mary (Beth) E Major | 2017-06-06 |  | 2018-08-16
Whalebone Solar | RE0000243 | Permit - Active | Solar | 3 | 40 |  |  |  |  | YES | No | Caroline County | No | Susan M Tripp | 2022-09-20 |  |  | 2022-09-20 |  |  |  | 2022-11-04
White Stone Ocran Solar | RE0000256 | Permit - Active | Solar | 5 | 184 |  |  |  | 40 | YES |  | Lancaster County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
White Stripe Solar LLC | RE0000187 | NOI - Withdrawn | Solar | 14 | 100 |  |  |  |  | No |  | Henry County | No | Mary (Beth) E Major | 2020-12-04 |  | 2021-04-05
Whitehorn Solar LLC | RE0000106 | Permit - Active | Solar | 50 | 704 | 0 |  | 0 | 410 | No | No | Pittsylvania County | No | Mary (Beth) E Major | 2019-06-10 |  |  | 2020-02-03 |  |  |  | 2020-04-22 |  |  | 2020-09-24 | 2021-12-01
Whitmell Solar, LLC | RE0000120 | Permit - Active | Solar | 5 | 171 |  |  |  |  | YES | No | Danville City | No | Mary (Beth) E Major | 2019-04-04 | [6 empty] | 2019-05-07
Wildcats Solar | RE0000308 | Permit - Active | Solar | 10 | 179 |  |  |  | 100 | YES | No | Wise County | YES | Amber K Foster | 2024-02-08 |  |  | 2024-02-08 | 2024-02-13 |  |  | 2024-03-15
Willow Solar Project | RE0000267 | Permit - Active | Solar | 12 | 149 |  |  |  | 78 | No | YES | Franklin County | No | Susan M Tripp | 2022-12-16 |  |  | 2023-10-03 |  | 2023-12-13 |  | 2023-12-14
Windsor PV1 | RE0000119 | NOI - Withdrawn | Solar | 85 | 573 |  |  |  |  | No | No | Isle of Wight County | No | Mary (Beth) E Major | 2019-10-15 |  | 2022-10-27
Windsor Solar | RE0000253 | Permit - Active | Solar | 85 | 1398 |  |  |  | 529 | No | YES | Isle of Wight County | No | Amber K Foster | 2022-11-02 |  |  | 2023-04-14 | 2023-05-31 | 2023-10-16 |  | 2023-12-06 | 2025-01-08 | 2025-03-06
Winterpock Solar I, LLC | RE0000171 | NOI - Withdrawn | Solar | 20 | 250 |  |  |  |  | No | No | Chesterfield County | No | Mary (Beth) E Major | 2019-11-22 |  | 2021-06-24
Wood Brothers Road Solar | RE0000214 | Permit - Active | Solar | 3 | 61 |  |  |  | 44 | YES |  | Middlesex County | No | Mary (Beth) E Major | 2021-11-01 |  |  | 2021-11-01 |  |  |  | 2021-12-16
Woodridge Solar | RE0000269 | Permit - Active | Solar | 138 | 2265 |  |  |  | 850 | No | YES | Albemarle County | No | Susan M Tripp | 2023-01-20 |  |  | 2024-05-23 |  | 2024-07-15 |  | 2024-07-23
Wythe BESS | RE0000316 | NOI - Active | Energy Storage | 52 | 12 |  |  |  |  | No |  | Wythe County | No | Amber K Foster | 2024-06-12
Wythe County Solar Project, LLC | RE0000104 | Permit - Active | Solar | 75 | 858 | 0 |  | 0 | 844 | No | No | Wythe County | No | Mary (Beth) E Major | 2019-11-21 |  |  | 2020-07-23 |  |  |  | 2020-09-22

## Apps-In Review
Data as of 3/11/2025
Permit Name | Permit Number | Project Status | Permit Type | Megawatts | Total Acres | Agricultural Land Acres | Pollinator Acres | Forestry Acres | Disturbance Zone Acres | Section 130 Permit | Mitigation Plan | County | Brownfield Site | Permit Coordinator | NOI Received | NOI Resubmittal Date(s) | NOI Withdrawn | Application Received | Application Incomplete | Supplemental Info from Applicant | Public Meeting Date | PBR Authorization Letter | PBR Modification Materials Received | PBR Modification Issued | Construction Commenced | Commercial Operation Commenced
Gateway Grid Battery Storage Facility Project | RE0000329 | Application - In Review | Energy Storage | 100 | 51 |  |  |  | 14 | No |  | Botetourt County | No | Amber K Foster | 2024-09-24 |  |  | 2025-02-13 | 2025-02-14
Prince Edward Solar Farm | RE0000246 | Application - In Review | Solar | 25 | 304 |  |  |  | 194 | No | No | Prince Edward County | No | Matthew A Snow | 2022-10-26 |  |  | 2025-01-31 |  |  | 2024-11-06

## Apps-Incomplete
Data as of 3/11/2025
Permit Name | Permit Number | Project Status | Permit Type | Megawatts | Total Acres | Agricultural Land Acres | Pollinator Acres | Forestry Acres | Disturbance Zone Acres | Section 130 Permit | Mitigation Plan | County | Brownfield Site | Permit Coordinator | NOI Received | NOI Resubmittal Date(s) | NOI Withdrawn | Application Received | Application Incomplete | Supplemental Info from Applicant | Public Meeting Date | PBR Authorization Letter | PBR Modification Materials Received | PBR Modification Issued | Construction Commenced | Commercial Operation Commenced
None

## NOIs-Active
Data as of 3/11/2025
Permit Name | Permit Number | Project Status | Permit Type | Megawatts | Total Acres | Agricultural Land Acres | Pollinator Acres | Forestry Acres | Disturbance Zone Acres | Section 130 Permit | Mitigation Plan | County | Brownfield Site | Permit Coordinator | NOI Received | NOI Resubmittal Date(s) | NOI Withdrawn | Application Received | Application Incomplete | Supplemental Info from Applicant | Public Meeting Date | PBR Authorization Letter | PBR Modification Materials Received | PBR Modification Issued | Construction Commenced | Commercial Operation Commenced
Amelia Solar Buckskin Creek Road | RE0000334 | NOI - Active | Solar | 106 | 1100 |  |  |  | 750 | No |  | Amelia County | No | Amber K Foster | 2024-10-25
Big Pine Solar | RE0000340 | NOI - Active | Solar | 150 | 2187 |  |  |  | 1050 | No |  | Sussex County | No | Matthew A Snow | 2024-12-02
Birchwood Renewables, LLC | RE0000201 | NOI - Active | Solar | 55 | 640 |  |  |  |  | No |  | King George County | YES | Mary (Beth) E Major | 2021-06-21
Blue Orchard Solar | RE0000208 | NOI - Active | Solar | 10 | 96 |  |  |  |  | No |  | Carroll County | No | Mary (Beth) E Major | 2021-10-05
BM&D Ltd. | RE0000031 | NOI - Active | Solar | 40 | 320 | 0 |  | 0 | 0 | No | No | Pulaski County | No | Mary (Beth) E Major | 2016-12-21
Boston Hill Solar Project | RE0000327 | NOI - Active | Solar | 115 | 1066 |  |  |  | 600 | No |  | Cumberland County | No | Amber K Foster | 2024-08-07
Buckhorn Mountain Solar Project | RE0000207 | NOI - Active | Solar | 16.5 | 465 |  |  |  |  | No |  | Tazewell County | No | Mary (Beth) E Major | 2021-10-01
Bumblebee Solar, LLC | RE0000072 | NOI - Active | Solar | 15 | 544 | 0 |  | 0 | 260 | No | No | Campbell County | No | Mary (Beth) E Major | 2017-11-08
Cabin Point Solar Center | RE0000152 | NOI - Active | Solar | 75 | 700 |  |  |  | 488 | No | No | Sussex County | No | Mary (Beth) E Major | 2020-02-18
Caden Energix Jarratt LLC | RE0000112 | NOI - Active | Solar | 82.5 | 695 | 0 |  | 0 | 0 | No | No | Greensville County | No | Mary (Beth) E Major | 2019-08-28
Caden Energix New Kent, LLC | RE0000151 | NOI - Active | Solar | 20 | 540 |  |  |  |  | No | No | New Kent County | No | Mary (Beth) E Major | 2020-01-24
Caden Energix Spout Spring LLC | RE0000097 | NOI - Active | Solar | 60 | 375 | 0 |  | 0 | 0 | No | No | Appomattox County | No | Mary (Beth) E Major | 2018-11-14
Chester Solar Technology Park, LLC | RE0000156 | NOI - Active | Solar | 150 | 1675 |  |  |  |  | No | No | Chesterfield County | No | Mary (Beth) E Major | 2020-03-18
Children of Chesterfield Solar | RE0000094 | NOI - Active | Solar | 20 | 165 | 0 |  | 0 | 135 | No | No | Chesterfield County | No | Mary (Beth) E Major | 2018-10-16
Colonial Solar | RE0000230 | NOI - Active | Solar | 7 | 90 |  |  |  |  | No |  | Prince William County | No | Susan M Tripp | 2022-05-27
Cox Energy Storage Project | RE0000287 | NOI - Active | Energy Storage | 8 | 1 |  |  |  |  | No |  | Cumberland County | No | Amber K Foster | 2023-05-26
Culpeper North Solar, LLC | RE0000070 | NOI - Active | Solar | 20 | 395 | 0 |  | 0 | 296 | No | No | Culpeper County | No | Mary (Beth) E Major | 2017-10-31
Cumberland Solar Project | RE0000326 | NOI - Active | Solar | 100 | 1794 |  |  |  | 900 | No |  | Cumberland County | No | Amber K Foster | 2024-08-07
Evergreen Energy Center | RE0000307 | NOI - Active | Energy Storage | 20 | 3 |  |  |  |  | YES |  | Loudoun County | No | Amber K Foster
Fairy Stone Solar | RE0000218 | NOI - Active | Solar | 12 | 316 |  |  |  | 169 | No |  | Patrick County | No | Mary (Beth) E Major | 2021-12-10
Fluvanna Middle School Solar Facility | RE0000217 | NOI - Active | Solar | 0.7 | 7 |  |  |  |  | YES |  | Fluvanna County | No | Mary (Beth) E Major | 2021-12-13
HCE Collier Solar | RE0000335 | NOI - Active | Solar | 7.5 | 160 |  |  |  |  | No |  | Wise County | No | Matthew A Snow | 2024-11-19
HCE Cropp Solar | RE0000336 | NOI - Active | Solar | 6.8 | 55 |  |  |  |  | No |  | Stafford County | No | Matthew A Snow | 2024-11-19
HCE Maddens Tavern Solar | RE0000337 | NOI - Active | Solar | 9.5 | 78 |  |  |  |  | No |  | Culpeper County | No | Matthew A Snow | 2024-11-19
HCE Mountain Run Solar | RE0000338 | NOI - Active | Solar | 7.5 | 74 |  |  |  |  | No |  | Culpeper County | No | Matthew A Snow | 2024-11-19
Hera Solar | RE0000328 | NOI - Active | Solar | 20 | 720 |  |  |  |  | No |  | Tazewell County | No | Amber K Foster | 2024-09-23
High Bridge Solar | RE0000321 | NOI - Active | Solar | 12 | 131 |  |  |  |  | No |  | Prince Edward County | No | Amber K Foster | 2024-06-26
Kangaroo Solar, LLC | RE0000183 | NOI - Active | Solar | 14.5 | 137 |  |  |  |  | No |  | Campbell County | No | Mary (Beth) E Major | 2020-12-04
Koala Solar, LLC | RE0000182 | NOI - Active | Solar | 14.5 | 131 |  |  |  |  | No |  | Campbell County | No | Mary (Beth) E Major | 2020-12-04
Loblolly Solar, LLC | RE0000086 | NOI - Active | Solar | 150 | 1384 | 0 |  | 0 | 0 | No | No | Surry County | No | Mary (Beth) E Major | 2018-09-07
Maples Solar | RE0000231 | NOI - Active | Solar | 15 | 200 |  |  |  |  | No |  | Fauquier County | No | Susan M Tripp | 2022-05-27
Moraticco Road Solar 1 | RE0000148 | NOI - Active | Solar | 20 | 50 |  |  |  |  | No | No | Lancaster County | No | Mary (Beth) E Major | 2019-12-02
Mount Nebo Solar Partners, LLC | RE0000101 | NOI - Active | Solar | 20 | 80 | 0 |  | 0 | 0 | No | No | Surry County | No | Mary (Beth) E Major | 2019-02-06
Mountain Pine Arvonia I & II | RE0000332 | NOI - Active | Solar | 80 | 1065 |  |  |  | 572 | No |  | Buckingham County | No | Matthew A Snow | 2024-10-18
Mt. Jackson Solar II, LLC | RE0000096 | NOI - Active | Solar | 19 | 175 | 0 |  | 0 | 0 | No | No | Shenandoah County | No | Mary (Beth) E Major | 2018-11-09
Mt. Jackson Solar III, LLC | RE0000124 | NOI - Active | Solar | 16.2 | 130 |  |  |  |  | No | No | Shenandoah County | No | Mary (Beth) E Major | 2018-11-09
North Ridge Culpeper Solar | RE0000266 | NOI - Active | Solar | 26 | 345 |  |  |  |  | No |  | Culpeper County | No | Susan M Tripp | 2022-12-12
Oral Oaks Road Solar | RE0000333 | NOI - Active | Solar | 12 | 128 |  |  |  |  | No |  | Lunenburg County | No | Matthew A Snow | 2024-10-16 | [5 empty] | 2024-11-18
Palmer Solar Center, LLC | RE0000142 | NOI - Active | Solar | 5 | 41 |  |  |  |  | YES | No | Fluvanna County | No | Mary (Beth) E Major | 2017-06-06
Partridge Creek Solar | RE0000285 | NOI - Active | Solar | 10 | 141 |  |  |  | 90 | No |  | Amherst County | No | Amber K Foster | 2023-05-18
Piney River Solar | RE0000282 | NOI - Active | Solar | 50 | 431 |  |  |  | 180 | No |  | Amherst County | No | Amber K Foster | 2023-04-13
Port Conway Solar, LLC | RE0000053 | NOI - Active | Solar | 20 | 250 | 0 |  | 0 | 0 | No | No | King George County | No | Mary (Beth) E Major | 2017-06-07
Quarry Energy Center | RE0000320 | NOI - Active | Energy Storage | 20 | 3 |  |  |  |  | YES |  | Lynchburg City | No | Amber K Foster | 2024-06-25
RER Hopewell Battery Energy Storage | RE0000294 | NOI - Active | Energy Storage | 40 | 1 |  |  |  |  | YES | No | Hopewell City | YES | Amber K Foster | 2023-08-15
SB Solar, LLC | RE0000068 | NOI - Active | Solar | 10 | 185 | 0 |  | 0 | 0 | No | No | Halifax County | No | Mary (Beth) E Major | 2017-10-16
Sedge Hill Solar | RE0000318 | NOI - Active | Solar | 80 | 1130 |  |  |  | 812 | No |  | Halifax County | No | Amber K Foster | 2024-06-26
Seven Bridges Solar | RE0000144 | NOI - Active | Solar | 116 | 2550 |  |  |  |  | No | No | Mecklenburg County | No | Amber K Foster | 2019-11-26
Sigora Solar | RE0000051 | NOI - Active | Solar | 40 | 126 | 0 |  | 0 | 0 | No | No | Wythe County | No | Mary (Beth) E Major | 2017-05-24
SolUnesco Racehorse | RE0000025 | NOI - Active | Solar | 15 | 90 | 0 |  | 0 | 0 | No | No | Caroline County | No | Mary (Beth) E Major | 2016-11-04
Spout Springs Solar LLC | RE0000036 | NOI - Active | Solar | 20 | 85 | 0 |  | 0 | 0 | No | No | Appomattox County | No | Mary (Beth) E Major | 2017-02-08
Springfield Farm Solar | RE0000283 | NOI - Active | Solar | 80 | 326 |  |  |  | 938 | No |  | Hanover County | No | Susan M Tripp | 2023-04-24
Stagecoach Solar, LLC | RE0000064 | NOI - Active | Solar | 15 | 318 | 0 |  | 0 | 0 | No | No | Halifax County | No | Mary (Beth) E Major | 2017-08-31
Staunton Solar | RE0000202 | NOI - Active | Solar | 47 | 300 |  |  |  | 65 | No |  | Halifax County | No | Mary (Beth) E Major | 2021-07-01
Staunton Utility Solar Project | RE0000292 | NOI - Active | Solar | 11 | 95 |  |  |  | 65 | No |  | Staunton City | No | Amber K Foster | 2023-07-25 | [5 empty] | 2025-03-13
Sunfish Solar | RE0000306 | NOI - Active | Solar | 80 | 932 |  |  |  | 588 | No |  | Orange County | No | Amber K Foster | 2024-01-19
SunPower Corporation, James City | RE0000027 | NOI - Active | Solar | 35 | 225 | 0 |  | 0 | 0 | No | No | James City County | No | Mary (Beth) E Major | 2016-10-25
SunPower Corporation, Southampton | RE0000022 | NOI - Active | Solar | 91 | 525 | 0 |  | 0 | 0 | No | No | Southampton County | No | Mary (Beth) E Major | 2016-10-18
SunPower Garden Fresh Produce | RE0000206 | NOI - Active | Solar | 6.4 | 58 |  |  |  |  | No |  | Rockingham County | No | Mary (Beth) E Major | 2021-09-30
SunTec Solar ESVA One, LLC | RE0000008 | NOI - Active | Solar | 80 | 500 | 0 |  | 0 | 0 | No | No | Accomack County | No | Mary (Beth) E Major | 2016-03-19
Surry Solar Center, LLC | RE0000223 | NOI - Active | Solar | 20 | 225 |  |  |  |  | No |  | Surry County | No | Susan M Tripp | 2022-03-31
Sweetspire, LLC | RE0000046 | NOI - Active | Solar | 20 | 165 | 0 |  | 0 | 0 | No | No | Hanover County | No | Mary (Beth) E Major | 2017-04-21
Tasley Energy Storage | RE0000342 | NOI - Active | Energy Storage | 10 | 1 |  |  |  |  | YES |  | Accomack County | No | Matthew A Snow | 2024-12-02
TPE Pamplin2 Solar | RE0000078 | NOI - Active | Solar | 16 | 309 | 0 |  | 0 | 0 | No | No | Prince Edward County | No | Mary (Beth) E Major | 2018-01-22
Turkey Solar, LLC | RE0000184 | NOI - Active | Solar | 14 | 141 |  |  |  |  | No |  | Louisa County | No | Mary (Beth) E Major | 2020-12-04
VA Sinai Solar | RE0000284 | NOI - Active | Solar | 9.9 | 100 |  |  |  |  | No |  | Halifax County | No | Amber K Foster | 2023-04-12
VSF Solar 1, LLC | RE0000085 | NOI - Active | Solar | 20 | 114 | 0 |  | 0 | 0 | No | No | Westmoreland County | No | Mary (Beth) E Major | 2018-08-16
VSF Solar 2, LLC | RE0000099 | NOI - Active | Solar | 11 | 100 | 0 |  | 0 | 0 | No | No | Westmoreland County | No | Mary (Beth) E Major | 2018-11-21
Waterloo Solar | RE0000229 | NOI - Active | Solar | 20 | 234 |  |  |  | 125 | No |  | Prince William County | No | Amber K Foster | 2023-05-22 | 2023-05-22 |  |  |  |  | 2024-11-05
Wythe BESS | RE0000316 | NOI - Active | Energy Storage | 52 | 12 |  |  |  |  | No |  | Wythe County | No | Amber K Foster | 2024-06-12

## NOIs-Withdrawn
Data as of 3/11/2025
Permit Name | Permit Number | Project Status | Permit Type | Megawatts | Total Acres | Agricultural Land Acres | Pollinator Acres | Forestry Acres | Disturbance Zone Acres | Section 130 Permit | Mitigation Plan | County | Brownfield Site | Permit Coordinator | NOI Received | NOI Resubmittal Date(s) | NOI Withdrawn | Application Received | Application Incomplete | Supplemental Info from Applicant | Public Meeting Date | PBR Authorization Letter | PBR Modification Materials Received | PBR Modification Issued | Construction Commenced | Commercial Operation Commenced
Bedford Solar Center, LLC | RE0000089 | NOI - Withdrawn | Solar | 70 | 475 | 0 |  | 0 | 0 | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2018-09-21 |  | 2019-08-15
Belcher Solar, LLC - Expansion Project | RE0000126 | NOI - Withdrawn | Solar | 17 | [5 empty] | No | YES | Louisa County | No | Mary (Beth) E Major | 2019-03-11 |  | 2019-09-20
Bookers Mill Solar, LLC | RE0000170 | NOI - Withdrawn | Solar | 127 | 1000 |  |  |  |  | No | No | Richmond County | No | Mary (Beth) E Major | 2020-06-11 |  | 2021-03-10
Brandy Station | RE0000034 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Culpeper County | No | Mary (Beth) E Major | 2017-02-07 |  | 2017-10-31
Caden Energix Piney River LLC | RE0000154 | NOI - Withdrawn | Solar | 50 | 389 |  |  |  |  | No | No | Amherst County | No | Mary (Beth) E Major | 2020-02-23 |  | 2023-09-06
Campari Solar, LLC | RE0000180 | NOI - Withdrawn | Solar | 15.6 | 141 |  |  |  |  | No |  | Orange County | No | Mary (Beth) E Major | 2020-12-04 |  | 2022-04-11
Centerville Pike Solar Project, LLC | RE0000010 | NOI - Withdrawn | Solar | 15 | 245 | 0 |  | 0 | 0 | No | No | Chesapeake City | No | Mary (Beth) E Major | 2016-04-05 |  | 2019-08-15
Chesapeake Solar, LLC | RE0000080 | NOI - Withdrawn | Solar | 20 | 250 |  |  |  |  | No |  | Chesapeake City | No | Mary (Beth) E Major | 2016-02-23 |  | 2016-09-29
Colonial Trail West Solar, LLC | RE0000032 | NOI - Withdrawn | Solar | 150 | 1250 | 0 |  | 0 | 0 | No | YES | Surry County | No | Mary (Beth) E Major | 2017-01-05 |  | 2017-03-14
Core Solar SPV XIII, LLC | RE0000050 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2017-05-23 |  | 2018-06-15
Endless Caverns Solar | RE0000077 | NOI - Withdrawn | Solar | 32 | 243 | 0 |  | 0 | 0 | No | No | Rockingham County | No | Mary (Beth) E Major | 2017-12-21 |  | 2022-04-18
First Solar Development, LLC | RE0000041 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Montgomery County | No | Mary (Beth) E Major | 2017-03-06 |  | 2019-03-19
Fort Powhatan Solar, LLC | RE0000115 | NOI - Withdrawn | Solar | 150 | 2000 | 0 |  | 0 | 0 | No | YES | Prince George County | No | Mary (Beth) E Major | 2018-04-11 |  | 2019-10-09
Fountain Creek Solar | RE0000102 | NOI - Withdrawn | Solar | 80 | 802 | 0 |  | 0 | 0 | No | No | Greensville County | No | Mary (Beth) E Major | 2019-02-19 |  | 2021-01-07
Gladys Solar Project | RE0000110 | NOI - Withdrawn | Solar | 60 | 1108 | 0 |  | 0 | 0 | No | No | Campbell County | No | Mary (Beth) E Major | 2019-08-28 |  | 2023-10-13
Grassfield Solar LLC | RE0000109 | NOI - Withdrawn | Solar | 20 | 100 | 0 |  | 0 | 0 | No | No | Chesapeake City | No | Mary (Beth) E Major | 2019-07-10 |  | 2020-05-26
Greenwood Solar I, LLC | RE0000059 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Culpeper County | No | Mary (Beth) E Major | 2017-07-20 |  | 2018-10-08
Halifax Solar, LLC | RE0000035 | NOI - Withdrawn | Solar | 15 | 125 | 0 |  | 0 | 0 | No | YES | Halifax County | No | Mary (Beth) E Major | 2017-02-08 |  | 2019-10-29
HCE Amelia Solar I, LLC | RE0000103 | NOI - Withdrawn | Solar | 10 | 60 | 0 |  | 0 | 0 | No | No | Amelia County | No | Mary (Beth) E Major | 2019-04-17 |  | 2020-05-06
Hickory Solar 1 LLC | RE0000121 | NOI - Withdrawn | Solar | 20 | 90 |  |  |  |  | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2017-02-08 |  | 2018-08-02
Hickory Solar 2 LLC | RE0000122 | NOI - Withdrawn | Solar | 15 | 60 |  |  |  |  | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2017-02-08 |  | 2018-08-02
Ho-Fel Solar Project | RE0000091 | NOI - Withdrawn | Solar | 39 | 292 | 0 |  | 0 | 0 | No | No | Isle of Wight County | No | Mary (Beth) E Major | 2018-10-02 |  | 2022-03-28
Ladybug Solar, LLC | RE0000067 | NOI - Withdrawn | Solar | 65 | 478 | 0 |  | 0 | 0 | No | YES | Mecklenburg County | No | Mary (Beth) E Major | 2017-10-16 |  | 2019-07-10
Lily Pond Solar, LLC | RE0000105 | NOI - Withdrawn | Solar | 83 | 2000 | 0 |  | 0 | 0 | No | No | Dinwiddie County | No | Mary (Beth) E Major | 2019-05-15 |  | 2022-04-08
Maplewood Solar I, LLC | RE0000058 | NOI - Withdrawn | Solar | 120 | 1200 | 0 |  | 0 | 0 | No | YES | Pittsylvania County | No | Mary (Beth) E Major | 2017-07-20 |  | 2019-10-10
Michaux Solar Center, LLC | RE0000199 | NOI - Withdrawn | Solar | 50 | 600 |  |  |  |  | No |  | Henry County | No | Mary (Beth) E Major | 2021-03-25 |  | 2023-04-06
Naples Solar, LLC | RE0000181 | NOI - Withdrawn | Solar | 14 | 126 |  |  |  |  | No |  | Orange County | No | Mary (Beth) E Major | 2020-12-04 |  | 2022-04-11
Piney Creek Solar | RE0000087 | NOI - Withdrawn | Solar | 80 | 700 | 0 |  | 0 | 0 | No | No | Halifax County | No | Mary (Beth) E Major | 2018-09-07 |  | 2021-03-01
Reservoir Solar LLC, | RE0000062 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Louisa County | No | Mary (Beth) E Major | 2017-07-25 |  | 2017-10-31
Rochambeau Solar, LLC | RE0000114 | NOI - Withdrawn | Solar | 19.9 | 192 | 0 |  | 0 | 0 | No | No | James City County | No | Mary (Beth) E Major | 2019-09-11 |  | 2019-12-20
Sadler Solar | RE0000100 | NOI - Withdrawn | Solar | 102 | 1490 | 0 |  | 0 | 0 | No | No | Greensville County | No | Mary (Beth) E Major | 2019-02-06 |  | 2020-06-01
Smithfield Solar Farm | RE0000009 | NOI - Withdrawn | Solar | 14 | 122 | 0 |  | 0 | 0 | No | No | Isle of Wight County | No | Mary (Beth) E Major | 2016-03-29 |  | 2024-10-30
Solar Access Development Group, LLC | RE0000020 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Culpeper County | No | Mary (Beth) E Major | 2016-08-15 |  | 2017-02-09
Solidago, LLC | RE0000047 | NOI - Withdrawn | Solar | 20 | 160 | 0 |  | 0 | 0 | No | No | Isle of Wight County | No | Mary (Beth) E Major | 2017-04-21 |  | 2021-05-05
SolUnesco Jefferson | RE0000026 | NOI - Withdrawn | Solar | 11 | 71 | 0 |  | 0 | 0 | No | YES | Albemarle County | No | Mary (Beth) E Major | 2016-11-04 |  | 2019-06-19
SolUnesco Leatherwood | RE0000024 | NOI - Withdrawn | Solar | 20 | 120 | 0 |  | 0 | 0 | No | YES | Henry County | No | Mary (Beth) E Major | 2016-11-04 |  | 2018-05-21
SolUnesco Locust Grove | RE0000023 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Orange County | No | Mary (Beth) E Major | 2016-11-04 |  | 2018-06-18
Spring Grove Solar I, LLC | RE0000073 | NOI - Withdrawn | Solar | 150 | 1338 | 0 |  | 0 | 0 | No | No | Surry County | No | Mary (Beth) E Major | 2017-11-09 |  | 2020-06-01
Spring Grove Solar, LLC | RE0000042 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Surry County | No | Mary (Beth) E Major | 2017-03-14 |  | 2017-11-09
Stratford Solar Center, LLC | RE0000153 | NOI - Withdrawn | Solar | 15 | 150 |  |  |  |  | No | No | Suffolk City | No | Mary (Beth) E Major | 2020-02-18 |  | 2020-09-22
Sun Ridge Solar | RE0000238 | NOI - Withdrawn | Solar | 50 | 564 |  |  |  |  | No |  | Rockingham County | YES | Susan M Tripp | 2022-08-15 |  | 2023-05-09
Sweet Sue Solar LLC | RE0000155 | NOI - Withdrawn | Solar | 77 | 576 |  |  |  |  | No | No | King William County | No | Mary (Beth) E Major | 2020-03-12 |  | 2021-11-22
Sycamore Solar I, LLC | RE0000057 | NOI - Withdrawn | Solar | 42 | 420 | 0 |  | 0 | 0 | No | No | Pittsylvania County | No | Mary (Beth) E Major | 2017-07-20 |  | 2020-07-28
TWE Chesapeake Solar Project, LLC | RE0000012 | NOI - Withdrawn | Solar | 15 | 175 | 0 |  | 0 | 0 | No | No | Chesapeake City | No | Mary (Beth) E Major | 2016-03-31 |  | 2019-08-15
Walnut Solar I, LLC | RE0000056 | NOI - Withdrawn | Solar | 150 | 1800 | 0 |  | 0 | 0 | No | No | King and Queen County | No | Mary (Beth) E Major | 2017-07-20 |  | 2021-08-09
Waverly Solar, LLC | RE0000082 | NOI - Withdrawn | Solar | 118 | 2000 | 0 |  | 0 | 0 | No | No | Sussex County | No | Mary (Beth) E Major | 2018-07-02 |  | 2022-03-18
Westmoreland Solar, LLC | RE0000052 | NOI - Withdrawn | Solar | 0 | 0 | 0 |  | 0 | 0 | No | YES | Westmoreland County | No | Mary (Beth) E Major | 2017-06-06 |  | 2018-08-16
White Stripe Solar LLC | RE0000187 | NOI - Withdrawn | Solar | 14 | 100 |  |  |  |  | No |  | Henry County | No | Mary (Beth) E Major | 2020-12-04 |  | 2021-04-05
Windsor PV1 | RE0000119 | NOI - Withdrawn | Solar | 85 | 573 |  |  |  |  | No | No | Isle of Wight County | No | Mary (Beth) E Major | 2019-10-15 |  | 2022-10-27
Winterpock Solar I, LLC | RE0000171 | NOI - Withdrawn | Solar | 20 | 250 |  |  |  |  | No | No | Chesterfield County | No | Mary (Beth) E Major | 2019-11-22 |  | 2021-06-24

## Permits-Issued
Data as of 3/11/2025
Permit Name | Permit Number | Project Status | Permit Type | Megawatts | Total Acres | Agricultural Land Acres | Pollinator Acres | Forestry Acres | Disturbance Zone Acres | Section 130 Permit | Mitigation Plan | County | Brownfield Site | Permit Coordinator | NOI Received | NOI Resubmittal Date(s) | NOI Withdrawn | Application Received | Application Incomplete | Supplemental Info from Applicant | Public Meeting Date | PBR Authorization Letter | PBR Modification Materials Received | PBR Modification Issued | Construction Commenced | Commercial Operation Commenced
1650 Cumberland Site 2 | RE0000301 | Permit - Active | Solar | 2 | 100 |  |  |  | 12 | YES | No | Cumberland County | No | Amber K Foster | 2023-10-24 |  |  | 2023-10-24 |  |  |  | 2023-10-25
1650 Cumberland Solar Facility | RE0000249 | Permit - Active | Solar | 3 | 101 |  |  |  | 20 | YES |  | Cumberland County | No | Susan M Tripp | 2022-10-21 |  |  | 2022-10-20 | 2022-10-27 |  |  | 2022-11-03
1671 Cumberland Solar Facility | RE0000248 | Permit - Active | Solar | 3 | 66 |  |  |  | 36 | YES |  | Prince Edward County | No | Susan M Tripp | 2022-10-21 |  |  | 2022-11-03
2188 Poorhouse Road Solar | RE0000254 | Permit - Active | Solar | 3 | 76 |  |  |  | 23 | YES |  | Lunenburg County | No | Amber K Foster | 2022-11-03 |  |  | 2022-11-03 |  |  |  | 2022-11-07
360 Solar Center Project | RE0000235 | Permit - Active | Solar | 52 | 800 |  |  |  | 450 | No | YES | Chesterfield County | No | Amber K Foster | 2022-07-19 |  |  | 2024-04-29 |  | 2024-05-08 | 2024-04-17 | 2024-07-15
Aditya Solar | RE0000186 | Permit - Active | Solar | 11 | 90 |  |  |  | 60 | No | No | Louisa County | No | Mary (Beth) E Major | 2021-01-15 |  |  | 2022-03-24 |  |  | 2022-03-07 | 2022-06-03 |  |  |  | 2023-08-21
Altavista Solar LLC (FKA Dragonfly) | RE0000088 | Permit - Active | Solar | 80 | 1200 | 0 |  | 0 | 0 | No | YES | Campbell County | No | Mary (Beth) E Major | 2018-09-12 |  |  | 2019-05-31 |  |  |  | 2019-08-08 |  |  | 2020-03-11 | 2021-06-04
Alton Post Office Solar, LLC | RE0000065 | Permit - Active | Solar | 75 | 768 | 0 |  | 0 | 501 | No | No | Halifax County | No | Mary (Beth) E Major | 2017-10-06 |  |  | 2020-09-15 |  |  |  | 2020-12-07 |  |  | 2023-09-20 | 2024-12-24
Amherst Mays Solar Farm | RE0000193 | Permit - Active | Solar | 4.9 | 50 |  |  |  | 25 | YES |  | Amherst County | No | Mary (Beth) E Major | 2021-01-26 |  |  | 2022-04-27 |  |  |  | 2022-05-03
Apple Grove Solar | RE0000162 | Permit - Active | Solar | 15 | 225 |  |  |  | 111 | No | YES | Louisa County | No | Susan M Tripp | 2020-05-22 |  |  | 2021-11-09 |  | 2022-02-18 |  | 2022-03-18 |  |  | 2023-03-27 | 2023-12-29
Ash Camp Solar, LLC | RE0000131 | Permit - Active | Solar | 1.6 | 11 |  |  |  |  | YES | No | Charlotte County | No | Mary (Beth) E Major | 2018-05-11 | [6 empty] | 2018-06-11
Augusta CSG LLC | RE0000244 | Permit - Active | Solar | 2.9 | 50 |  |  |  | 12 | YES |  | Augusta County | No | Susan M Tripp | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Axton Solar | RE0000111 | Permit - Active | Solar | 66 | 600 | 0 |  | 0 | 547 | No | YES | Henry County | No | Susan M Tripp | 2019-08-28 |  |  | 2022-03-23 |  |  | 2022-03-08 | 2022-06-17 |  |  | 2022-10-03 | 2023-12-28
BARC Community Solar Project | RE0000132 | Permit - Active | Solar | 0.5 | 5 |  |  |  |  | YES | No | Bath County | No | Mary (Beth) E Major | 2015-11-13
Bartonsville Energy Facility II, LLC | RE0000221 | Permit - Active | Solar | 50 | 478 |  |  |  | 407 | No | YES | Frederick County | No | Susan M Tripp | 2022-02-17 |  |  | 2022-06-21 | 2022-09-14 | 2022-09-16 | 2022-06-06 | 2022-09-23 |  |  | 2022-09-26
Bartonsville Energy Facility, LLC | RE0000158 | Permit - Active | Solar | 80 | 1160 |  |  |  | 869 | No | No | Frederick County | No | Mary (Beth) E Major | 2020-03-18 | 2020-10-14 |  | 2021-08-16 |  |  |  | 2021-11-01
Bedford Solar Center | RE0000146 | Permit - Active | Solar | 70 | 566 |  |  |  | 410 | No | No | Chesapeake City | No | Mary (Beth) E Major | 2019-11-20 |  |  | 2020-01-14 |  |  |  | 2020-04-09 |  |  | 2020-07-30 | 2021-11-23
Bedford Solar, LLC | RE0000133 | Permit - Active | Solar | 3 | 100 |  |  |  | 22 | YES | No | Bedford County | No | Mary (Beth) E Major | 2017-03-13 | [6 empty] | 2017-03-23
Belcher Solar, LLC | RE0000028 | Permit - Active | Solar | 88.2 | 1305 | 0 |  | 0 | 0 | No | YES | Louisa County | No | Mary (Beth) E Major | 2016-10-28 |  |  | 2017-06-20 |  |  |  | 2017-08-08 |  |  | 2020-01-14 | 2021-06-30
Bella Terra Solar | RE0000213 | Permit - Active | Solar | 100 | 1056 |  |  |  | 558 | No | YES | Pulaski County | No | Amber K Foster | 2021-12-06 |  |  | 2023-02-17 | 2023-04-25 | 2023-08-25 | 2024-10-15 | 2023-10-24 | 2024-11-11 | 2025-01-10
Blue Rock Solar | RE0000298 | Permit - Active | Solar | 100 | 596 |  |  |  | 1127 | No | No | Buckingham County | No | Amber K Foster | 2023-09-19 |  |  | 2024-12-27 |  |  | 2024-08-27 | 2025-02-06
Bluestone Farm Solar, LLC | RE0000014 | Permit - Active | Solar | 50 | 333 | 0 |  | 0 | 0 | No | No | Mecklenburg County | No | Mary (Beth) E Major | 2016-05-13 |  |  | 2017-10-25 |  |  |  | 2017-12-05 |  |  | 2019-03-01 | 2021-06-01
Bookers Mill Solar | RE0000196 | Permit - Active | Solar | 127 | 1600 |  |  |  | 640 | No |  | Richmond County | No | Mary (Beth) E Major | 2021-03-10 |  |  | 2021-09-01 |  |  |  | 2021-11-29 |  |  | 2022-08-01
Bowie Road Solar, LLC | RE0000322 | Permit - Active | Solar | 5 | 20 |  |  |  |  | YES |  | Westmoreland County | No | Matthew A Snow | 2024-07-15 |  |  | 2024-07-15 |  |  |  | 2024-07-17
Briel Farm Solar LLC | RE0000039 | Permit - Active | Solar | 20 | 230 | 0 |  | 0 | 105 | No | YES | Henrico County | No | Mary (Beth) E Major | 2017-02-15 |  |  | 2018-04-11 |  | 2018-04-24 |  | 2018-06-14 | 2020-01-17 | 2020-03-10 |  | 2021-03-02
Buchanan County Solar Project | RE0000346 | Permit - Active | Solar | 75 | 1188 |  |  |  |  | YES | No | Buchanan County | YES | Amber K Foster | 2025-02-27 |  |  | 2025-02-27 | 2025-02-27 |  |  | 2025-03-03
Buckingham II Solar LLC | RE0000063 | Permit - Active | Solar | 20 | 295 | 0 |  | 0 | 225 | No | No | Buckingham County | No | Mary (Beth) E Major | 2017-07-25 |  |  | 2018-02-20 | 2018-03-29 |  |  | 2018-06-18 |  |  | 2020-10-07 | 2021-07-28
Buckingham Solar I, LLC | RE0000005 | Permit - Active | Solar | 19.8 | 302 | 0 |  | 0 | 200 | No | No | Buckingham County | No | Mary (Beth) E Major | 2016-02-18 |  |  | 2016-06-09 |  |  |  | 2016-08-09 |  |  | 2017-05-13 | 2017-11-30
Caden Energix Hickory, LLC | RE0000083 | Permit - Active | Solar | 32 | 154 | 0 |  | 0 | 145 | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2018-08-02 |  |  | 2018-11-26 |  | 2019-01-21 |  | 2019-03-14 |  |  |  | 2020-08-18
Caden Energix Wytheville LLC | RE0000113 | Permit - Active | Solar | 20 | 154 | 0 |  | 0 | 139 | No | No | Wythe County | No | Mary (Beth) E Major | 2019-08-28 |  |  | 2020-06-03 |  |  | 2020-05-05 | 2020-07-27 |  |  | 2021-09-27 | 2022-06-03
Carey and Peyton 5 | RE0000280 | Permit - Active | Solar | 5 | 56 |  |  |  | 39 | YES | No | Westmoreland County | No | Amber K Foster | 2023-03-17 |  |  | 2023-03-17 |  |  |  | 2023-03-27
Carver Solar I | RE0000305 | Permit - Active | Solar | 91 | 1138 |  |  |  | 637 | No | YES | Isle of Wight County | No | Amber K Foster | 2024-01-16 |  |  | 2024-11-22 |  | 2025-01-03 | 2024-11-07 | 2025-01-31
Carvers Creek Solar | RE0000145 | Permit - Active | Solar | 150 | 2400 |  |  |  | 1734 | No | YES | Gloucester County | No | Mary (Beth) E Major | 2019-11-22 |  |  | 2020-08-18 |  |  |  | 2020-11-12 |  |  | 2022-10-01 | 2024-12-23
Centerville South Solar | RE0000281 | Permit - Active | Solar | 5 | 39 |  |  |  | 31 | YES | No | Chesapeake City | No | Amber K Foster | 2023-03-21 |  |  | 2023-03-21 |  |  |  | 2023-03-27
Centerville Turnpike Solar Facility | RE0000250 | Permit - Active | Solar | 3 | 49 |  |  |  | 29 | YES |  | Chesapeake City | No | Susan M Tripp | 2022-11-03 |  |  | 2022-11-03 |  |  |  | 2023-01-05
Chaberton Solar Leatherman | RE0000315 | Permit - Active | Solar | 5 | 40 |  |  |  | 18 | YES | No | Hanover County | No | Amber K Foster | 2024-05-29 |  |  | 2024-05-29 | 2024-06-03 |  |  | 2024-12-16
Chesapeake Solar Project, LLC | RE0000006 | Permit - Active | Solar | 118 | 940 | 0 |  | 0 | 0 | No | YES | Chesapeake City | No | Mary (Beth) E Major | 2018-06-15 |  |  | 2021-11-02 |  |  | 2021-10-15 | 2022-01-14 |  |  | 2022-11-11 | 2023-12-20
Correctional Solar, LLC | RE0000016 | Permit - Active | Solar | 20 | 1690 | 0 |  | 0 | 460 | No | YES | Gloucester County | No | Mary (Beth) E Major | 2016-05-30 |  |  | 2016-08-29 |  |  |  | 2016-10-17 |  |  | 2017-05-01 | 2017-11-29
Courthouse Hwy Solar 1 | RE0000309 | Permit - Active | Solar | 3 | 14 |  |  |  | 5 | YES | No | Isle of Wight County | No | Amber K Foster | 2024-02-16 |  |  | 2024-02-14 | 2024-02-16 |  |  | 2024-02-23
Cow Creek Solar, LLC | RE0000194 | Permit - Active | Solar | 1 | 9 |  |  |  |  | YES |  | Gloucester County | No | Mary (Beth) E Major | 2021-01-04 |  |  | 2021-01-04 |  |  |  | 2021-04-02
Crystal Hill Solar, LLC | RE0000066 | Permit - Active | Solar | 65 | 629 | 0 |  | 0 | 0 | No | No | Halifax County | No | Mary (Beth) E Major | 2017-10-06 |  |  | 2019-10-09 |  |  |  | 2019-12-17 |  |  | 2023-03-08 | 2023-12-29
Cunningham Solar, LLC | RE0000205 | Permit - Active | Solar | 5 | 62 |  |  |  | 30 | YES |  | Fluvanna County | No | Mary (Beth) E Major | 2021-06-02 | [6 empty] | 2021-08-06
CVE Johnson North | RE0000297 | Permit - Active | Solar | 3 | 110 |  |  |  | 24 | YES | No | Suffolk City | No | Amber K Foster | 2023-09-15 |  |  | 2023-09-15 |  |  |  | 2023-09-22
CVE Johnson South | RE0000296 | Permit - Active | Solar | 5 | 137 |  |  |  | 29 | YES | No | Suffolk City | No | Amber K Foster | 2023-09-15 |  |  | 2023-09-15 |  |  |  | 2023-09-22
CVE Murphy Solar Project | RE0000313 | Permit - Active | Solar | 2.6 | 13 |  |  |  |  | YES | No | Petersburg City | No | Amber K Foster |  |  |  | 2024-05-15 | 2024-05-21 |  |  | 2024-05-22
Danville BESS 1 | RE0000240 | Permit - Active | Energy Storage | 10.5 | 1 |  |  |  |  | YES | No | Danville City | No | Susan M Tripp | 2022-08-09 |  |  | 2022-08-09 |  |  |  | 2022-10-14 |  |  | 2022-02-28
Danville Farm, LLC | RE0000084 | Permit - Active | Solar | 12 | 191 | 0 |  | 0 | 0 | No | No | Pittsylvania County | No | Mary (Beth) E Major | 2018-08-09 |  |  | 2019-05-09 |  |  |  | 2019-07-10 |  |  | 2019-12-15 | 2020-08-26
Depot Solar | RE0000090 | Permit - Active | Solar | 15 | 150 | 150 |  | 0 | 0 | No | No | Campbell County | No | Mary (Beth) E Major | 2018-09-21 |  |  | 2019-08-27 |  |  |  | 2019-11-05 |  |  |  | 2022-07-15
Dept. of Veterans Affairs Medical Center | RE0000137 | Permit - Active | Solar | 1.7 | 6 |  |  |  |  | YES | No | Salem City | No | Mary (Beth) E Major | 2013-07-02 | [6 empty] | 2013-07-09
DG Revolution Solar | RE0000325 | Permit - Active | Solar | 5 | 101 |  |  |  | 38 | YES |  | Richmond County | No | Amber K Foster | 2024-07-17 |  |  | 2024-07-17 | 2024-07-18 |  |  | 2024-07-19
Dogwood Lane Solar | RE0000262 | Permit - Active | Solar | 4 | 33 |  |  |  |  | YES | No | Lunenburg County | No | Amber K Foster | 2022-11-29 |  |  | 2022-11-29 |  |  |  | 2022-12-08
Dry Fork Solar 1 | RE0000270 | Permit - Active | Solar | 3 | 47 |  |  |  | 21 | YES | No | Pittsylvania County | No | Amber K Foster | 2023-01-18 |  |  | 2023-01-18 |  |  |  | 2023-01-24
E2C Solar | RE0000138 | Permit - Active | Solar | 1.3 | 9 |  |  |  |  | YES | No | Montgomery County | No | Mary (Beth) E Major | 2017-07-12 | [6 empty] | 2017-07-12
Eastern Shore Solar, LLC | RE0000001 | Permit - Active | Solar | 80 | 1003 | 0 |  | 0 | 942 | No | YES | Accomack County | No | Mary (Beth) E Major | 2014-10-14 |  |  | 2015-06-08 |  |  |  | 2015-09-28 |  |  | 2015-09-28 | 2016-10-30
Elam Road Solar | RE0000303 | Permit - Active | Solar | 3 | 135 |  |  |  | 33 | YES | No | Prince Edward County | No | Amber K Foster | 2023-10-19 |  |  | 2023-10-19 |  |  |  | 2023-11-17
Endless Caverns North | RE0000227 | Permit - Active | Solar | 15.7 | 171 |  |  |  | 105 | No | YES | Rockingham County | No | Susan M Tripp | 2022-05-06 |  |  | 2022-12-12 |  | 2023-03-03 | 2022-11-29 | 2023-03-14 |  |  | 2023-05-22 | 2024-03-12
Endless Caverns South | RE0000232 | Permit - Active | Solar | 15.7 | 142 |  |  |  | 99 | No | YES | Rockingham County | No | Susan M Tripp | 2022-05-06 |  |  | 2022-12-08 |  | 2023-02-22 | 2022-11-21 | 2023-03-14 |  |  | 2023-05-22 | 2024-03-05
Energix Nokesville, LLC | RE0000061 | Permit - Active | Solar | 20 | 300 | 0 |  | 0 | 0 | No | YES | Prince William County | No | Mary (Beth) E Major | 2017-07-25 |  |  | 2019-05-21 | 2019-07-30 | 2019-12-17 |  | 2020-02-20 |  |  | 2021-10-26 | 2024-05-20
Essex Solar Center LLC | RE0000007 | Permit - Active | Solar | 20 | 419 | 0 |  | 0 | 174 | No | YES | Essex County | No | Mary (Beth) E Major | 2016-03-02 |  |  | 2016-10-11 |  |  |  | 2016-12-07 | 2019-12-04 | 2020-03-05 | 2017-05-12 | 2017-12-14
Exmore Energy Storage EXENST10MW | RE0000341 | Permit - Active | Energy Storage | 10 | 2 |  |  |  | 1 | YES | No | Northampton County | No | Matthew A Snow | 2024-12-02 |  |  | 2024-12-02 | 2025-01-17 |  |  | 2025-01-24
Fairfax Landfill Solar | RE0000331 | Permit - Active | Solar | 5 | 40 |  |  |  | 31 | YES |  | Fairfax County | YES | Amber K Foster | 2024-09-05 |  |  | 2024-09-05 |  |  |  | 2024-10-03
Fairfield Lee Solar | RE0000260 | Permit - Active | Solar | 5 | 46 |  |  |  | 29 | YES | No | Rockbridge County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Fisher Chewning Solar | RE0000224 | Permit - Active | Solar | 150 | 1620 |  |  |  | 1365 | No | YES | Louisa County | No | Susan M Tripp | 2022-04-04 |  |  | 2022-06-15 |  | 2022-09-09 | 2022-06-01 | 2022-10-07
Fort Powhatan Solar, LLC | RE0000125 | Permit - Active | Solar | 150 | 3086 |  |  |  | 2000 | No | YES | Prince George County | No | Mary (Beth) E Major | 2019-10-07 |  |  | 2020-01-09 |  |  |  | 2020-03-19 |  |  | 2020-08-03 | 2022-01-19
Foxglove Solar, LLC | RE0000172 | Permit - Active | Solar | 75 | 672 |  |  |  | 408 | No | YES | Frederick County | No | Mary (Beth) E Major | 2020-08-28 |  |  | 2021-04-19 |  | 2021-06-07 |  | 2021-08-04 | 2022-05-02 | 2022-07-26 | 2023-08-21 | 2024-10-10
Foxhound Solar | RE0000095 | Permit - Active | Solar | 83 | 1125 | 0 |  | 0 | 600 | No | YES | Halifax County | No | Mary (Beth) E Major | 2018-10-26 |  |  | 2019-09-11 |  |  | 2019-07-02 | 2019-12-17 | 2020-01-15 | 2020-01-16 | 2023-01-17
Front Royal Solar Field | RE0000139 | Permit - Active | Solar | 2.5 | 20 |  |  |  | 15 | YES | No | Warren County | No | Mary (Beth) E Major | 2016-09-06 | [6 empty] | 2016-09-06 |  |  |  | 2017-03-31
Gardy's Mill Solar, LLC | RE0000043 | Permit - Active | Solar | 14 | 199 | 0 |  | 0 | 0 | No | No | Westmoreland County | No | Mary (Beth) E Major | 2017-04-18 |  |  | 2018-09-05 |  |  |  | 2018-11-27 |  |  |  | 2020-12-01
Gladys Solar LLC | RE0000299 | Permit - Active | Solar | 60.4 | 1108 |  |  |  | 615 | No | YES | Campbell County | No | Amber K Foster | 2023-10-13 |  |  | 2024-01-25 | 2024-01-31 | 2024-03-07 |  | 2024-03-08
Gloucester Solar, LLC | RE0000048 | Permit - Active | Solar | 20 | 204 | 0 |  | 0 | 0 | No | YES | Gloucester County | No | Mary (Beth) E Major | 2017-04-27 |  |  | 2017-11-30 |  |  |  | 2018-02-12 | 2019-11-26 | 2020-03-19 | 2018-08-18 | 2019-04-22
Grasshopper Solar, LLC | RE0000029 | Permit - Active | Solar | 80 | 927 | 0 |  | 0 | 913 | No | YES | Mecklenburg County | No | Mary (Beth) E Major | 2016-11-21 |  |  | 2019-05-09 |  |  |  | 2019-09-05 |  |  | 2019-09-25 | 2020-09-29
Green Acres Solar, LLC | RE0000176 | Permit - Active | Solar | 5 | 36 |  |  |  |  | YES |  | Henry County | YES | Mary (Beth) E Major | 2020-11-09 |  |  | 2020-11-09 |  |  |  | 2021-02-05
Greensville County Solar Project | RE0000093 | Permit - Active | Solar | 80 | 1125 | 0 |  | 0 | 646 | No | YES | Greensville County | No | Mary (Beth) E Major | 2018-10-10 |  |  | 2019-07-18 |  |  |  | 2019-10-15 |  |  | 2019-12-20 | 2020-12-01
Greenwood Solar I, LLC | RE0000123 | Permit - Active | Solar | 100 | 1384 |  |  |  | 1000 | No | YES | Culpeper County | No | Mary (Beth) E Major | 2018-10-08 |  |  | 2020-07-28 |  |  |  | 2020-09-22
Halifax CSG Solar | RE0000255 | Permit - Active | Solar | 3.1 | 43 |  |  |  |  | YES |  | Halifax County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Harris Road Solar 1 Facility | RE0000251 | Permit - Active | Solar | 3 | 119 |  |  |  | 33 | YES | No | Lancaster County | No | Susan M Tripp | 2022-11-03 |  |  | 2022-11-03 |  |  |  | 2022-11-07
Harris Road Solar 2 Facility | RE0000252 | Permit - Active | Solar | 2 | 119 |  |  |  | 23 | YES |  | Lancaster County | No | Susan M Tripp | 2022-10-21 |  |  | 2022-11-03 |  |  |  | 2022-11-07
Haynesville Correctional Center | RE0000134 | Permit - Active | Solar | 0.6 | 136 |  |  |  | 5 | YES | No | Richmond County | No | Mary (Beth) E Major | 2018-04-19 | [6 empty] | 2018-06-11
HCE Amelia Solar I | RE0000159 | Permit - Active | Solar | 5 | 98 |  |  |  | 32 | YES | No | Amelia County | No | Mary (Beth) E Major | 2020-05-11 |  |  | 2020-05-11 |  |  |  | 2020-06-17
HCE Amelia Solar II | RE0000166 | Permit - Active | Solar | 5 | 190 |  |  |  | 30 | YES | No | Amelia County | No | Mary (Beth) E Major | 2020-05-11 |  |  | 2020-05-11 |  |  |  | 2020-06-17
HCE Bustleburg Solar | RE0000178 | Permit - Active | Solar | 2.5 | 90 |  |  |  | 15 | YES |  | Rockbridge County | No | Mary (Beth) E Major | 2020-09-18 |  |  | 2020-09-18 |  |  |  | 2021-02-05
HCE Millboro Springs Solar | RE0000160 | Permit - Active | Solar | 5 | 23 |  |  |  |  | YES | No | Bath County | No | Mary (Beth) E Major | 2020-05-11 |  |  | 2020-05-11 |  |  |  | 2020-06-17
HCE Moran Solar | RE0000168 | Permit - Active | Solar | 3 | 154 |  |  |  | 18 | YES | No | Prince Edward County | No | Mary (Beth) E Major | 2020-05-29 |  |  | 2020-05-29 |  |  |  | 2020-06-17
HCE Powhatan Solar | RE0000165 | Permit - Active | Solar | 5 | 40 |  |  |  |  | YES | No | Powhatan County | No | Mary (Beth) E Major | 2020-05-11 |  |  | 2020-05-11 |  |  |  | 2020-06-17
HCE Reams Solar | RE0000179 | Permit - Active | Solar | 5 | 62 |  |  |  | 35 | YES |  | Dinwiddie County | No | Mary (Beth) E Major | 2020-11-30 |  |  | 2020-11-30 |  |  |  | 2021-02-05
HCE Red House Solar, LLC | RE0000164 | Permit - Active | Solar | 5 | 110 |  |  |  | 33 | YES | No | Charlotte County | No | Mary (Beth) E Major | 2020-05-11 |  |  | 2020-05-11 |  |  |  | 2020-06-17 |  |  | 2021-08-12
HCE Roark Mill Solar | RE0000161 | Permit - Active | Solar | 3 | 230 |  |  |  | 20 | YES | No | Pittsylvania County | No | Mary (Beth) E Major | 2020-05-18 |  |  | 2020-05-18 |  |  |  | 2020-06-17
HEC Acorn Solar Facility | RE0000210 | Permit - Active | Solar | 1.4 | 9 |  |  |  |  | YES |  | Harrisonburg City | No | Mary (Beth) E Major | 2021-11-30 |  |  | 2021-11-30 |  |  |  | 2022-01-21
Hecate Energy Cherrydale | RE0000003 | Permit - Active | Solar | 20 | 236 | 0 |  | 0 | 0 | No | No | Northampton County | No | Mary (Beth) E Major | 2015-10-13 |  |  | 2016-07-13 |  |  |  | 2016-08-15 |  |  | 2017-03-30 | 2017-10-25
Hecate Energy Clarke County, LLC | RE0000004 | Permit - Active | Solar | 20 | 235 | 0 |  | 0 | 0 | No | YES | Clarke County | No | Mary (Beth) E Major | 2015-10-13 |  |  | 2016-08-18 |  |  |  | 2016-09-22 |  |  | 2017-02-15 | 2017-07-26
Hemings Solar | RE0000195 | Permit - Active | Solar | 4.9 | 86 |  |  |  | 35 | YES |  | Richmond County | No | Mary (Beth) E Major | 2021-01-27 |  |  | 2021-03-08 |  |  |  | 2021-03-08
Ho-Fel Solar | RE0000225 | Permit - Active | Solar | 40 | 350 |  |  |  |  | No | YES | Isle of Wight County | No | Susan M Tripp | 2022-03-30 |  |  | 2023-03-27 |  | 2023-05-23 | 2023-03-14 | 2023-06-08
Hollyfield | RE0000049 | Permit - Active | Solar | 17 | 160 | 0 |  | 0 | 0 | No | No | King William County | YES | Mary (Beth) E Major | 2017-05-19 |  |  | 2017-08-15 |  |  |  | 2017-10-02 |  |  | 2017-10-10 | 2018-09-06
Hollyfield II Solar, LLC | RE0000040 | Permit - Active | Solar | 13 | 231 | 0 |  | 0 | 170 | No | YES | King William County | YES | Mary (Beth) E Major | 2017-03-03 |  |  | 2018-01-29 |  |  |  | 2018-03-29 |  |  | 2020-07-14 | 2021-07-22
Impact Power Solutions / Larry Davis Solar | RE0000271 | Permit - Active | Solar | 1.8 | 50 |  |  |  | 13 | YES | No | Buckingham County | No | Amber K Foster | 2023-02-03 |  |  | 2023-02-13 |  |  |  | 2023-02-17
Impact Power Solutions / NCN Properties 3 | RE0000272 | Permit - Active | Solar | 2 | 21 |  |  |  | 13 | YES | No | Buckingham County | No | Amber K Foster | 2023-02-03 |  |  | 2023-01-27 |  |  |  | 2023-02-17
Impact Power Solutions / Self 4 – Inez Smith | RE0000273 | Permit - Active | Solar | 4.5 | 64 |  |  |  | 27 | YES | No | Richmond County | No | Amber K Foster | 2023-01-27 |  |  | 2023-01-27 |  |  |  | 2023-02-17
Impact Power Solutions / Town of Gretna I | RE0000275 | Permit - Active | Solar | 1 | 138 |  |  |  | 5 | YES | No | Pittsylvania County | No | Amber K Foster | 2023-02-13 |  |  | 2023-02-10 |  |  |  | 2023-02-17
James Energy Center | RE0000319 | Permit - Active | Energy Storage | 20 | 3 |  |  |  |  | YES |  | Lynchburg City | No | Amber K Foster | 2024-06-25 |  |  | 2024-12-13 | 2024-12-16 |  |  | 2025-01-06
Jarratt Energy Facility | RE0000157 | Permit - Active | Solar | 49 | 500 |  |  |  |  | No | No | Greensville County | No | Susan M Tripp | 2020-03-18 |  |  | 2022-05-26 |  |  |  | 2022-08-24
Jouett Elementary School | RE0000188 | Permit - Active | Solar | 0.8 | 4 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2020-11-18 |  |  | 2021-02-02 |  |  |  | 2021-03-05
KDC Solar Kings Creek, LLC | RE0000130 | Permit - Active | Solar | 20 | 395 |  |  |  | 200 | YES | No | James City County | YES | Mary (Beth) E Major | 2019-10-31 |  |  | 2019-10-31 |  |  |  | 2019-11-05
Kentuck Solar, LLC | RE0000013 | Permit - Active | Solar | 6 | 77 | 0 |  | 0 | 0 | YES | No | Pittsylvania County | No | Mary (Beth) E Major | 2016-04-27 | [6 empty] | 2016-08-29
King William Solar, LLC | RE0000167 | Permit - Active | Solar | 1.5 | 4 |  |  |  |  | YES | No | King William County | No | Mary (Beth) E Major | 2020-03-04 |  |  | 2020-03-04 |  |  |  | 2020-06-10
Kinglet Solar | RE0000304 | Permit - Active | Solar | 5 | 172 |  |  |  | 40 | YES | No | Stafford County | No | Amber K Foster | 2023-11-21 |  |  | 2023-11-21 | 2023-11-22 |  |  | 2023-12-01
Knollwood Halifax Solar | RE0000277 | Permit - Active | Solar | 5 | 140 |  |  |  | 50 | YES | No | Halifax County | No | Amber K Foster | 2023-03-15 |  |  | 2023-03-15 |  |  |  | 2023-03-17
Land of Promise Solar, LLC | RE0000323 | Permit - Active | Solar | 5 | 135 |  |  |  | 21 | YES |  | Chesapeake City | No | Matthew A Snow | 2024-07-15 |  |  | 2024-07-15 |  |  |  | 2024-07-16
Louisa County Middle School Solar Facility | RE0000192 | Permit - Active | Solar | 1.3 | 5 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2020-11-18 |  |  | 2021-02-02 |  |  |  | 2021-03-05
Maplewood Solar | RE0000149 | Permit - Active | Solar | 120 | 1850 |  |  |  | 1556 | No | YES | Pittsylvania County | No | Mary (Beth) E Major | 2019-11-27 |  |  | 2020-03-16 |  |  |  | 2020-06-10 |  |  | 2020-07-20 | 2022-12-19
Martin Solar Center, LLC | RE0000140 | Permit - Active | Solar | 5 | 114 |  |  |  | 35 | YES | No | Fluvanna County | No | Mary (Beth) E Major | 2017-06-06 | [6 empty] | 2017-06-06 |  |  |  | 2017-12-01
Martin Trail Farm Solar | RE0000265 | Permit - Active | Solar | 5 | 40 |  |  |  |  | YES | No | Halifax County | No | Amber K Foster | 2022-11-29 |  |  | 2022-11-29 |  |  |  | 2022-12-08
Martinsville Solar, LLC | RE0000200 | Permit - Active | Solar | 8 | 55 |  |  |  |  | YES |  | Martinsville City | YES | Mary (Beth) E Major | 2021-04-12 | [6 empty] | 2021-06-03
Mechanicsville Solar, LLC | RE0000021 | Permit - Active | Solar | 25 | 250 | 0 |  | 0 | 0 | No | YES | Hanover County | No | Mary (Beth) E Major | 2016-09-12 |  |  | 2017-08-08 |  |  |  | 2017-09-26 | 2020-05-06 | 2020-05-18 | 2019-12-09 | 2020-06-10
Midway Solar, LLC | RE0000203 | Permit - Active | Solar | 8 | 136 |  |  |  | 80 | No | YES | Albemarle County | No | Amber K Foster | 2021-06-25 |  |  | 2022-11-28 |  | 2023-02-16 | 2021-11-03 | 2023-03-07
Mine & Hemmer Solar | RE0000239 | Permit - Active | Solar | 94 | 460 |  |  |  | 229 | No | YES | Louisa County | No | Susan M Tripp | 2022-08-05 |  |  | 2023-03-10 |  | 2023-04-12 | 2023-02-22 | 2023-06-01
Mineral Gap Data Center | RE0000220 | Permit - Active | Solar | 3 | 14 |  |  |  |  | YES | No | Wise County | YES | Mary (Beth) E Major | 2021-02-23 | [6 empty] | 2022-01-13
Monroe Solar | RE0000177 | Permit - Active | Solar | 2.2 | 62 |  |  |  | 35 | YES |  | Pittsylvania County | No | Mary (Beth) E Major | 2020-11-04 |  |  | 2020-11-04 |  |  |  | 2021-02-05
Montross Solar | RE0000075 | Permit - Active | Solar | 20 | 337 | 0 |  | 0 | 120 | No | YES | Westmoreland County | No | Mary (Beth) E Major | 2017-11-30 |  |  | 2018-02-16 |  |  |  | 2018-05-17 |  |  | 2018-07-20 | 2018-12-12
Moody Creek Solar, LLC | RE0000118 | Permit - Active | Solar | 150 | 1631 |  |  |  | 798 | No | YES | Charlotte County | No | Mary (Beth) E Major | 2019-10-21 |  |  | 2021-03-12 |  | 2021-04-14 |  | 2021-06-01
Moseley Hermon Solar | RE0000311 | Permit - Active | Solar | 5 | 135 |  |  |  | 32 | YES |  | Chesterfield County | No | Amber K Foster | 2023-05-10 | 2024-12-03 |  | 2023-05-10 | 2024-02-22 |  |  | 2024-12-04
Moss Nuckols Elementary School | RE0000185 | Permit - Active | Solar | 0.8 | 4 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2020-11-18 |  |  | 2021-02-02 |  |  |  | 2021-03-05
Mt Jackson Solar I, LLC | RE0000044 | Permit - Active | Solar | 16 | 185 | 0 |  | 0 | 0 | No | YES | Shenandoah County | No | Mary (Beth) E Major | 2017-04-20 |  |  | 2017-12-28 | 2018-03-01 |  |  | 2018-07-17 |  |  |  | 2021-06-14
Muskie Solar | RE0000241 | Permit - Active | Solar | 4.9 | 398 |  |  |  | 40 | YES |  | Caroline County | No | Amber K Foster | 2022-07-21 |  |  | 2022-07-21 |  |  |  | 2022-09-09
Nansemond Solar | RE0000317 | Permit - Active | Solar | 5 | 40 |  |  |  | 36 | YES | No | Suffolk City | No | Amber K Foster | 2024-06-11 |  |  | 2024-06-11 |  |  |  | 2024-06-16
NASA Wallops Flight Facility - Main Base | RE0000141 | Permit - Active | Solar | 3.5 | 26 |  |  |  |  | YES | No | Accomack County | No | Mary (Beth) E Major | 2018-12-03 | [6 empty] | 2018-12-17
NASA Wallops Flight Facility Phase 3B | RE0000163 | Permit - Active | Solar | 4.9 | 26 |  |  |  |  | YES | No | Accomack County | No | Mary (Beth) E Major | 2020-02-05 | [6 empty] | 2020-02-21
North Branch Solar | RE0000339 | Permit - Active | Solar | 3 | 147 |  |  |  | 40 | YES | No | Prince Edward County | No | Amber K Foster | 2024-11-26 |  |  | 2024-11-07 | 2024-11-26 |  |  | 2024-12-05
Nuby Run Solar | RE0000288 | Permit - Active | Solar | 2 | 178 |  |  |  | 27 | YES | No | Isle of Wight County | No | Amber K Foster | 2023-06-29 |  |  | 2023-06-29 |  |  |  | 2023-07-11 |  |  | 2023-06-28
Pamplin Solar, LLC | RE0000038 | Permit - Active | Solar | 15.7 | 112 | 0 |  | 0 | 82 | No | YES | Appomattox County | No | Mary (Beth) E Major | 2017-02-08 |  |  | 2018-06-15 |  |  |  | 2018-08-28 |  |  |  | 2020-07-13
Peppertown Road Solar | RE0000295 | Permit - Active | Solar | 5 | 32 |  |  |  | 19 | YES |  | Hanover County | No | Amber K Foster | 2023-09-06 |  |  | 2023-08-31 | 2023-09-06 |  |  | 2023-10-11
Pigeon Run Solar, LLC | RE0000136 | Permit - Active | Solar | 60 | 612 |  |  |  | 296 | No | YES | Campbell County | No | Mary (Beth) E Major | 2019-11-19 |  |  | 2021-04-26 |  |  |  | 2021-08-04
Pittsylvania CSG Solar | RE0000258 | Permit - Active | Solar | 3.8 | 52 |  |  |  | 14 | YES | No | Pittsylvania County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Pleasant Hill Solar | RE0000098 | Permit - Active | Solar | 20 | 208 | 0 |  | 0 | 180 | No | No | Suffolk City | No | Mary (Beth) E Major | 2018-11-20 |  |  | 2020-11-13 |  |  | 2020-10-13 | 2021-02-05
Pocaty River Solar, LLC | RE0000324 | Permit - Active | Solar | 2 | 27 |  |  |  | 9 | YES |  | Chesapeake City | No | Matthew A Snow | 2024-07-15 |  |  | 2024-07-15 |  |  |  | 2024-07-17
Powell Creek Solar | RE0000264 | Permit - Active | Solar | 5 | 631 |  |  |  | 47 | YES | No | Prince George County | No | Amber K Foster | 2022-11-29 |  |  | 2022-11-29 |  |  |  | 2022-12-08
Powells Creek Farm Solar, LLC | RE0000045 | Permit - Active | Solar | 70 | 710 | 0 |  | 0 | 502 | No | YES | Halifax County | No | Mary (Beth) E Major | 2017-04-21 |  |  | 2019-02-13 |  |  |  | 2019-05-02 |  |  | 2022-08-16
Prairie Solar | RE0000291 | Permit - Active | Solar | 20 | 433 |  |  |  | 201 | No | YES | Isle of Wight County | No | Amber K Foster | 2023-06-30 |  |  | 2023-09-12 |  |  |  | 2023-10-27 |  |  | 2025-02-24
Prince Edward CSG Solar | RE0000259 | Permit - Active | Solar | 4 | 85 |  |  |  |  | YES | No | Prince Edward County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Prince Edward Solar 1 | RE0000276 | Permit - Active | Solar | 5 | 86 |  |  |  | 20 | YES | No | Prince Edward County | No | Amber K Foster | 2023-02-20 |  |  | 2023-02-20 |  |  |  | 2023-03-02
Prospect Power | RE0000312 | Permit - Active | Energy Storage | 150 | 25 |  |  |  |  | No | YES | Rockingham County | No | Amber K Foster | 2024-04-10 |  |  | 2024-09-10 |  | 2024-10-18 | 2024-08-27 | 2024-11-08
Pulaski I Solar | RE0000212 | Permit - Active | Solar | 150 | 1664 |  |  |  | 981 | No | YES | Pulaski County | No | Amber K Foster | 2021-12-06 |  |  | 2023-02-16 | 2023-04-25 | 2023-12-14 | 2022-10-18 | 2024-01-16
Puller Solar | RE0000060 | Permit - Active | Solar | 15 | 201 | 0 |  | 0 | 170 | No | YES | Middlesex County | No | Mary (Beth) E Major | 2017-07-21 |  |  | 2017-09-13 |  |  |  | 2017-12-12 |  |  | 2018-03-16 | 2018-12-05
Pumpkinseed Solar | RE0000054 | Permit - Active | Solar | 60 | 836 | 0 |  | 0 | 381 | No | No | Greensville County | No | Mary (Beth) E Major | 2017-06-14 | 2019-05-08 |  | 2019-10-07 |  |  |  | 2019-12-17 |  |  | 2020-12-02 | 2022-09-29
Randolf Solar | RE0000190 | Permit - Active | Solar | 3.2 | 91 |  |  |  | 35 | YES |  | Shenandoah County | No | Mary (Beth) E Major | 2021-01-27 |  |  | 2021-03-08 |  |  |  | 2021-03-08 |  |  | 2023-03-06
Rappahannock Solar, LLC | RE0000147 | Permit - Active | Solar | 1.5 | 184 |  |  |  | 17 | YES | No | Lancaster County | No | Mary (Beth) E Major | 2019-07-09 | [6 empty] | 2019-07-09 |  |  |  | 2021-11-01
Red Brick Solar | RE0000233 | Permit - Active | Solar | 130 | 1938 |  |  |  | 1309 | No | YES | Lunenburg County | No | Susan M Tripp | 2022-06-15 |  |  | 2022-10-25 |  | 2022-10-28 | 2022-09-07 | 2023-03-03
Reed Road Solar 1 | RE0000330 | Permit - Active | Solar | 4 | 26 |  |  |  | 19 | YES | No | Roanoke County | No | Amber K Foster | 2024-09-27 |  |  | 2024-09-27 |  |  |  | 2024-09-30
Richmond Road Solar | RE0000344 | Permit - Active | Solar | 5 | 61 |  |  |  | 134 | YES | No | James City County | No | Amber K Foster | 2024-12-30 |  |  | 2024-12-30 |  |  |  | 2025-01-02
Rivanna Solar, LLC | RE0000108 | Permit - Active | Solar | 12.5 | 150 | 0 |  | 0 | 71 | No | No | Albemarle County | No | Mary (Beth) E Major | 2019-06-19 |  |  | 2019-10-16 |  |  |  | 2020-01-16
River Trail Solar | RE0000219 | Permit - Active | Solar | 20 | 390 |  |  |  | 169 | No | YES | Carroll County | No | Amber K Foster | 2021-12-10 |  |  | 2022-12-19 |  | 2023-03-13 | 2022-12-07 | 2023-04-25 | 2023-06-09 | 2023-09-22 | 2024-01-22
Riverstone Solar | RE0000211 | Permit - Active | Solar | 149.5 | 1992 |  |  |  | 1819 | No | YES | Buckingham County | No | Susan M Tripp | 2021-11-29 |  |  | 2022-07-28 |  | 2022-10-25 | 2022-06-07 | 2022-11-29
Rives Road Solar, LLC | RE0000037 | Permit - Active | Solar | 19.7 | 147 | 0 |  | 0 | 0 | No | No | Prince George County | No | Mary (Beth) E Major | 2017-02-08 |  |  | 2018-04-11 | 2018-09-18 | 2019-01-08 |  | 2019-01-15 |  |  |  | 2020-06-01
Rochambeau Solar, LLC | RE0000150 | Permit - Active | Solar | 19.9 | 282 |  |  |  | 192 | No | YES | James City County | No | Mary (Beth) E Major | 2020-01-03 |  |  | 2020-03-13 |  |  | 2020-02-27 | 2020-05-12 |  |  | 2021-04-05 | 2021-12-23
Rocky Forge Wind, LLC | RE0000002 | Permit - Active | Wind | 80 | 200 | 0 |  | 0 | 0 | No | YES | Botetourt County | No | Mary (Beth) E Major | 2015-06-25 |  |  | 2016-05-03 |  |  |  | 2017-03-02 | 2020-08-25 | 2020-10-16 | 2021-03-18
Route 360 Solar | RE0000263 | Permit - Active | Solar | 5 | 40 |  |  |  |  | YES | No | Halifax County | No | Amber K Foster | 2022-11-29 |  |  | 2022-11-29 |  |  |  | 2022-12-08
Rye Cove Solar 1 | RE0000345 | Permit - Active | Solar | 4 | 197 |  |  |  | 35 | YES | No | Scott County | No | Amber K Foster | 2025-02-06 |  |  | 2025-02-06 |  |  |  | 2025-02-10
Sandale Solar | RE0000290 | Permit - Active | Solar | 3 | 58 |  |  |  | 23 | YES | No | Lancaster County | No | Amber K Foster | 2023-06-20 | [6 empty] | 2023-07-11
Scott II Solar LLC | RE0000018 | Permit - Active | Solar | 20 | 720 | 0 |  | 0 | 230 | No | No | Powhatan County | No | Mary (Beth) E Major | 2016-06-09 |  |  | 2016-10-11 |  |  |  | 2016-12-08 |  |  | 2017-04-25 | 2017-11-29
Scout Energy Storage Facility | RE0000237 | Permit - Active | Energy Storage | 80 | 10 |  |  |  |  | YES |  | Accomack County | No | Amber K Foster | 2022-08-05 |  |  | 2022-10-06 |  |  |  | 2023-01-03
Self I Solar LLC | RE0000268 | Permit - Active | Solar | 5 | 49 |  |  |  | 34 | YES | No | Richmond County | No | Amber K Foster | 2023-01-11 |  |  | 2023-01-12 |  |  |  | 2023-01-12
Shad Solar | RE0000236 | Permit - Active | Solar | 4.9 | 44 |  |  |  | 38 | YES |  | Caroline County | No | Amber K Foster | 2022-07-21 |  |  | 2022-07-21 |  |  |  | 2022-09-09
Shifting Sands Solar | RE0000234 | Permit - Active | Solar | 18.8 | 251 |  |  |  | 152 | No | YES | Henry County | No | Susan M Tripp | 2022-07-15 |  |  | 2023-03-03 |  |  | 2023-02-13 | 2023-05-16 |  |  | 2024-01-22
Shockoe Solar, LLC | RE0000173 | Permit - Active | Solar | 60 | 903 |  |  |  | 290 | No | YES | Pittsylvania County | No | Mary (Beth) E Major | 2020-09-09 |  |  | 2021-06-23 |  |  |  | 2021-10-21
Sol Leatherwood Solar, LLC | RE0000079 | Permit - Active | Solar | 20 | 322 | 0 |  | 0 | 0 | No | YES | Henry County | No | Mary (Beth) E Major | 2018-05-21 |  |  | 2018-10-18 |  |  |  | 2018-12-17 |  |  | 2021-01-08 | 2021-08-09
Sol Madison Solar, LLC | RE0000081 | Permit - Active | Solar | 62.5 | 355 | 0 |  | 0 | 0 | No | YES | Orange County | No | Mary (Beth) E Major | 2018-06-18 |  |  | 2019-02-05 |  |  |  | 2019-04-23 | 2020-04-21 | 2020-06-10 | 2021-07-26 | 2024-09-13
Solar Star Buchanan 2 | RE0000300 | Permit - Active | Solar | 4.5 | 405 |  |  |  | 23 | YES | No | Botetourt County | No | Amber K Foster | 2023-10-20 |  |  | 2023-10-20 | 2023-10-24 |  |  | 2023-11-14
Solar Star Petersburg 1 | RE0000274 | Permit - Active | Solar | 4.8 | 22 |  |  |  | 20 | YES |  | Petersburg City | No | Susan M Tripp | 2023-02-02 |  |  | 2023-02-02 |  |  |  | 2023-05-09
Solar VA 2019 LLC | RE0000198 | Permit - Active | Solar | 18 | 125 |  |  |  | 55 | No | YES | Westmoreland County | No | Susan M Tripp | 2021-03-19 |  |  | 2021-07-12 |  | 2022-06-17 |  | 2022-06-27
South Boston G Solar | RE0000314 | Permit - Active | Solar | 5 | 125 |  |  |  | 39 | YES |  | Halifax County | No | Amber K Foster | 2024-05-28 |  |  | 2024-05-28 |  |  |  | 2024-06-06
South Boston I Solar | RE0000302 | Permit - Active | Solar | 5 | 48 |  |  |  | 38 | YES | No | South Boston City | No | Amber K Foster | 2023-10-27 |  |  | 2023-10-27 | 2023-11-02 |  |  | 2023-11-09
Southampton Solar, LLC | RE0000015 | Permit - Active | Solar | 100 | 1200 | 0 |  | 0 | 0 | No | YES | Southampton County | No | Mary (Beth) E Major | 2016-05-16 |  |  | 2016-12-19 |  |  |  | 2017-01-24 |  |  | 2017-03-08 | 2017-11-26
Spring Grove Solar II, LLC | RE0000074 | Permit - Active | Solar | 150 | 1650 | 0 |  | 0 | 0 | No | No | Surry County | No | Mary (Beth) E Major | 2020-09-08 |  |  | 2020-12-11 |  |  |  | 2021-03-04
Staunton Community Solar Project | RE0000293 | Permit - Active | Solar | 5 | 95 |  |  |  | 25 | YES | No | Staunton City | No | Amber K Foster | 2023-07-27 |  |  | 2023-07-27 |  |  |  | 2023-07-28
Stratford Solar Center, LLC | RE0000175 | Permit - Active | Solar | 15 | 154 |  |  |  | 109 | No | YES | Suffolk City | No | Mary (Beth) E Major | 2020-09-24 |  |  | 2021-06-04 |  |  | 2021-04-04 | 2021-09-15 |  |  | 2022-01-31 | 2022-12-01
STS J. Hodges, LLC (Middlesex ES and MS) | RE0000128 | Permit - Active | Solar | 1 | 4 |  |  |  |  | YES | No | Middlesex County | No | Mary (Beth) E Major | 2019-08-08 |  |  | 2019-08-08 |  |  |  | 2019-11-18
STS Joan Bosch, LLC (Cople ES) | RE0000129 | Permit - Active | Solar | 0.7 | 3 |  |  |  |  | YES | No | Westmoreland County | No | Mary (Beth) E Major | 2019-08-08 |  |  | 2021-04-05 |  |  |  | 2021-04-05
Suffolk CSG Solar | RE0000257 | Permit - Active | Solar | 4 | 21 |  |  |  |  | YES | No | Suffolk City | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Sun Ridge Solar | RE0000286 | Permit - Active | Solar | 50 | 564 |  |  |  | 236 | No | YES | Rockingham County | No | Amber K Foster | 2023-05-08 |  |  | 2023-08-16 |  |  |  | 2023-11-08 |  |  | 2024-02-02
Sunny Rock Solar Project | RE0000278 | Permit - Active | Solar | 20 | 180 |  |  |  | 145 | No | YES | Henry County | No | Amber K Foster | 2023-03-07 |  |  | 2023-08-22 |  |  |  | 2023-11-20 |  |  | 2024-02-19
Sunnybrook Farm Solar, LLC | RE0000030 | Permit - Active | Solar | 51 | 352 | 0 |  | 0 | 242 | No | YES | Halifax County | No | Mary (Beth) E Major | 2016-12-09 |  |  | 2018-07-09 |  | 2018-09-21 |  | 2018-09-25 |  |  | 2022-01-27 | 2022-12-01
Sussex Drive Solar | RE0000017 | Permit - Active | Solar | 20 | 371 | 0 |  | 0 | 250 | No | No | Sussex County | No | Mary (Beth) E Major | 2016-06-09 |  |  | 2016-11-21 |  |  |  | 2017-01-12 |  |  | 2017-04-27 | 2017-11-30
Sweet Spring Solar | RE0000289 | Permit - Active | Solar | 1 | 116 |  |  |  | 19 | YES | No | Orange County | No | Amber K Foster | 2023-06-20 | [6 empty] | 2023-07-11
Sydnor Solar Farm | RE0000033 | Permit - Active | Solar | 3 | 50 | 0 |  | 0 | 20 | YES | No | Mecklenburg County | No | Mary (Beth) E Major | 2017-02-06
The Louisa County HIgh School Solar Facility | RE0000191 | Permit - Active | Solar | 1.8 | 7 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2020-11-18 |  |  | 2021-02-02 |  |  |  | 2021-03-05
Thomas Jefferson Elementary School Solar Facility | RE0000216 | Permit - Active | Solar | 0.5 | 7 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2021-10-27 | [6 empty] | 2021-10-27
Town of Gretna II | RE0000242 | Permit - Active | Solar | 4 | 63 |  |  |  | 24 | YES |  | Pittsylvania County | No | Susan M Tripp | 2022-08-31 |  |  | 2023-02-03 |  |  |  | 2023-02-17
TPE Irish Road Solar, LLC | RE0000127 | Permit - Active | Solar | 5 | 171 |  |  |  |  | YES | No | Danville City | No | Mary (Beth) E Major | 2019-04-04 | [6 empty] | 2019-05-07
Trevilians Elementary School | RE0000189 | Permit - Active | Solar | 0.6 | 3 |  |  |  |  | YES |  | Louisa County | No | Mary (Beth) E Major | 2020-11-18 |  |  | 2021-02-02 |  |  |  | 2021-03-05
Turner Solar, LLC | RE0000071 | Permit - Active | Solar | 20 | 581 | 0 |  | 0 | 463 | No | No | Henrico County | No | Mary (Beth) E Major | 2017-10-31 |  |  | 2018-11-29 | 2019-04-18 | 2019-05-28 |  | 2019-07-10
TWE Myrtle Solar Project, LLC | RE0000011 | Permit - Active | Solar | 15 | 135 | 0 |  | 0 | 110 | No | YES | Suffolk City | No | Mary (Beth) E Major | 2016-03-31 |  |  | 2018-02-12 |  |  |  | 2018-05-15 | 2020-01-15 | 2020-04-10 | 2020-01-29 | 2020-06-18
Twittys Creek Solar, LLC | RE0000019 | Permit - Active | Solar | 15 | 100 | 0 |  | 0 | 91 | No | No | Charlotte County | No | Mary (Beth) E Major | 2016-06-16 |  |  | 2017-10-19 |  |  |  | 2017-12-05 |  |  | 2020-06-12 | 2020-12-01
Two Oaks Solar | RE0000215 | Permit - Active | Solar | 118 | 1234 |  |  |  | 917 | No | YES | Louisa County | No | Amber K Foster | 2021-11-30 |  |  | 2024-03-11 | 2024-03-20 |  | 2024-02-28 | 2024-04-25
VA Cox Cartersville (Ampthill Rd) Solar Project | RE0000226 | Permit - Active | Solar | 16 | 86 |  |  |  | 80 | No | YES | Cumberland County | No | Susan M Tripp | 2022-04-22 |  |  | 2022-06-29 |  | 2022-09-19 | 2022-05-26 | 2022-11-23
Volvo Group North America LLC - NRV Plant | RE0000135 | Permit - Active | Wind | 4 | [5 empty] | YES | No | Pulaski County | No | Mary (Beth) E Major | 2013-09-10 | [6 empty] | 2013-09-16
Waller Solar | RE0000204 | Permit - Active | Solar | 131 | 2764 |  |  |  | 1200 | No | YES | Lancaster County | No | Mary (Beth) E Major | 2021-06-07 |  |  | 2023-01-06 |  | 2023-03-22 | 2022-12-14 | 2023-03-27
Warm Run Solar | RE0000343 | Permit - Active | Solar | 3 | 35 |  |  |  |  | YES |  | Rockbridge County | No | Matthew A Snow | 2024-12-16 |  |  | 2024-12-16 |  |  |  | 2024-12-19
Water Strider Solar, LLC | RE0000069 | Permit - Active | Solar | 80 | 1196 | 0 |  | 0 | 1042 | No | YES | Halifax County | No | Mary (Beth) E Major | 2017-10-16 |  |  | 2018-10-25 |  |  |  | 2019-04-30 |  |  | 2020-04-08 | 2021-05-15
Watlington Solar, LLC | RE0000169 | Permit - Active | Solar | 20 | 220 |  |  |  | 140 | No | No | Halifax County | No | Mary (Beth) E Major | 2020-06-17 |  |  | 2021-01-05 |  |  |  | 2021-03-17
Waverly I Solar | RE0000222 | Permit - Active | Solar | 50 | 2992 |  |  |  | 1177 | No | YES | Sussex County | No | Susan M Tripp | 2022-03-28 |  |  | 2022-06-27 |  |  | 2022-06-14 | 2022-10-05 |  |  | 2023-06-01 | 2024-03-14
Waverly II Solar | RE0000228 | Permit - Active | Solar | 68 | 1700 |  |  |  | 438 | No | YES | Sussex County | No | Susan M Tripp | 2022-04-25 |  |  | 2022-12-05 |  | 2023-02-03 | 2022-11-16 | 2023-03-03 |  |  | 2023-06-07 | 2024-03-14
Wayne Ave Solar 2 | RE0000310 | Permit - Active | Solar | 3 | 37 |  |  |  | 23 | YES | No | Augusta County | No | Amber K Foster | 2024-02-20 |  |  | 2024-02-14 | 2024-02-16 |  |  | 2024-02-23
Wayne Ave Solar Facility | RE0000247 | Permit - Active | Solar | 3 | 80 |  |  |  | 25 | YES |  | Augusta County | No | Susan M Tripp | 2022-11-03 |  |  | 2022-11-03
Waynesboro Bridge Solar | RE0000261 | Permit - Active | Solar | 5 | 90 |  |  |  | 40 | YES | No | Augusta County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Westmoreland County Solar Project | RE0000092 | Permit - Active | Solar | 20 | 161 | 0 |  | 0 | 100 | No | No | Westmoreland County | No | Mary (Beth) E Major | 2018-09-21 |  |  | 2019-11-04 |  |  |  | 2020-01-28 |  |  |  | 2021-10-01
Westmoreland CSG 1 | RE0000279 | Permit - Active | Solar | 5 | 80 |  |  |  | 22 | YES | No | Westmoreland County | No | Amber K Foster | 2023-03-17 |  |  | 2023-03-17 |  |  |  | 2023-03-27
Whalebone Solar | RE0000243 | Permit - Active | Solar | 3 | 40 |  |  |  |  | YES | No | Caroline County | No | Susan M Tripp | 2022-09-20 |  |  | 2022-09-20 |  |  |  | 2022-11-04
White Stone Ocran Solar | RE0000256 | Permit - Active | Solar | 5 | 184 |  |  |  | 40 | YES |  | Lancaster County | No | Amber K Foster | 2022-11-18 |  |  | 2022-11-18 |  |  |  | 2022-11-30
Whitehorn Solar LLC | RE0000106 | Permit - Active | Solar | 50 | 704 | 0 |  | 0 | 410 | No | No | Pittsylvania County | No | Mary (Beth) E Major | 2019-06-10 |  |  | 2020-02-03 |  |  |  | 2020-04-22 |  |  | 2020-09-24 | 2021-12-01
Whitmell Solar, LLC | RE0000120 | Permit - Active | Solar | 5 | 171 |  |  |  |  | YES | No | Danville City | No | Mary (Beth) E Major | 2019-04-04 | [6 empty] | 2019-05-07
Wildcats Solar | RE0000308 | Permit - Active | Solar | 10 | 179 |  |  |  | 100 | YES | No | Wise County | YES | Amber K Foster | 2024-02-08 |  |  | 2024-02-08 | 2024-02-13 |  |  | 2024-03-15
Willow Solar Project | RE0000267 | Permit - Active | Solar | 12 | 149 |  |  |  | 78 | No | YES | Franklin County | No | Susan M Tripp | 2022-12-16 |  |  | 2023-10-03 |  | 2023-12-13 |  | 2023-12-14
Windsor Solar | RE0000253 | Permit - Active | Solar | 85 | 1398 |  |  |  | 529 | No | YES | Isle of Wight County | No | Amber K Foster | 2022-11-02 |  |  | 2023-04-14 | 2023-05-31 | 2023-06-29 |  | 2023-12-06 | 2025-01-08 | 2025-03-06
Wood Brothers Road Solar | RE0000214 | Permit - Active | Solar | 3 | 61 |  |  |  | 44 | YES |  | Middlesex County | No | Mary (Beth) E Major | 2021-11-01 |  |  | 2021-11-01 |  |  |  | 2021-12-16
Woodridge Solar | RE0000269 | Permit - Active | Solar | 138 | 2265 |  |  |  | 850 | No | YES | Albemarle County | No | Susan M Tripp | 2023-01-20 |  |  | 2024-05-23 |  | 2024-07-15 |  | 2024-07-23
Wythe County Solar Project, LLC | RE0000104 | Permit - Active | Solar | 75 | 858 | 0 |  | 0 | 844 | No | No | Wythe County | No | Mary (Beth) E Major | 2019-11-21 |  |  | 2020-07-23 |  |  |  | 2020-09-22

## Permits-Term wo Cause
Data as of 3/11/2025
Permit Name | Permit Number | Project Status | Permit Type | Megawatts | Total Acres | Agricultural Land Acres | Pollinator Acres | Forestry Acres | Disturbance Zone Acres | Section 130 Permit | Mitigation Plan | County | Brownfield Site | Permit Coordinator | NOI Received | NOI Resubmittal Date(s) | NOI Withdrawn | Application Received | Application Incomplete | Supplemental Info from Applicant | Public Meeting Date | PBR Authorization Letter | PBR Modification Materials Received | PBR Modification Issued | Construction Commenced | Commercial Operation Commenced
Black Bear Solar, LLC | RE0000197 | Permit - Terminated without Cause | Solar | 1.6 | 13 |  |  |  |  | YES |  | Buckingham County | No | Mary (Beth) E Major | 2021-02-19 |  |  | 2021-02-19 |  |  |  | 2021-04-02
Carysbrook Solar | RE0000245 | Permit - Terminated without Cause | Solar | 3 | 360 |  |  |  | 40 | YES | No | Fluvanna County | No | Amber K Foster | 2022-10-18 |  |  | 2022-10-18 |  |  |  | 2022-10-28
Church View Solar, LLC | RE0000076 | Permit - Terminated without Cause | Solar | 20 | 535 | 0 |  | 0 | 0 | No | YES | Middlesex County | No | Mary (Beth) E Major | 2017-12-06 |  |  | 2018-02-02 | 2018-03-29 | 2018-03-19 |  | 2018-06-21
Dogwood Solar | RE0000107 | Permit - Terminated without Cause | Solar | 20 | 350 | 0 |  | 0 | 178 | No | YES | Page County | No | Mary (Beth) E Major | 2019-06-14 |  |  | 2021-10-12 |  |  |  | 2022-01-14
North Ridge Powhatan Solar LLC | RE0000174 | Permit - Terminated without Cause | Solar | 20 | 197 |  |  |  |  | No | No | Powhatan County | No | Mary (Beth) E Major | 2020-09-14 |  |  | 2021-07-28 |  |  |  | 2021-11-30
Otter Creek Solar, LLC | RE0000055 | Permit - Terminated without Cause | Solar | 60 | 685 | 0 |  | 0 | 0 | No | No | Mecklenburg County | No | Mary (Beth) E Major | 2017-06-14 |  |  | 2019-08-12 |  |  |  | 2019-10-24
Powhatan Solar I, LLC | RE0000143 | Permit - Terminated without Cause | Solar | 18 | 225 |  |  |  |  | No | YES | Powhatan County | No | Mary (Beth) E Major | 2019-11-21 |  |  | 2020-08-13 |  | 2020-10-20 |  | 2021-04-02
Redbud Run Solar Project | RE0000209 | Permit - Terminated without Cause | Solar | 30 | 263 |  |  |  | 150 | No | YES | Frederick County | No | Amber K Foster | 2021-10-21 |  |  | 2022-09-26 | 2022-12-22 | 2023-04-12 | 2022-09-06 | 2023-05-01